## Land_Parcel_Tracking
Parcel_ID | Project_ID | State | District | Taluka | Village | Survey_Number | Farmer_Name | Land_Area_Acres | Agreement_Status | Legal_Verification | Registration_Status | Payment_Status | Acquisition_Date
LND-0498 | PRJ-KA-05 | Karnataka | Gadag | Gadag | Betgeri | 74/1 | Hanumantha Biradar | 3.46 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0489 | PRJ-KA-08 | Karnataka | Bidar | Basavakalyan | Udgir | Gut No. 867/3 | Fakeerappa Angadi | 3.22 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0165 | PRJ-MH-02 | Maharashtra | Solapur | Mohol | Pandharpur | Gut No. 429/3 | Mahadev Murkute | 1.42 | Agreement Executed | Cleared | Not Registered | Partially Paid
LND-0109 | PRJ-MH-02 | Maharashtra | Osmanabad | Tuljapur | Wadgaon | Gut No. 622/8 | Mahadev Mane | 1.47 | Not Started | Pending | Not Registered | Unpaid
LND-0111 | PRJ-MH-01 | Maharashtra | Solapur | Barshi | Shegaon | 783/5 | Popat Salve | 1.04 | Agreement Executed | Disputed | Not Registered | Partially Paid
LND-0445 | PRJ-KA-02 | Karnataka | Gadag | Gadag | Betgeri | 890/5 | Basavaraj Hugar | 3.62 | Not Started | Pending | Not Registered | Unpaid
LND-0257 | PRJ-MH-07 | Maharashtra | Solapur | Barshi | Shegaon | Gut No. 938/6 | Santosh Jadhav | 3.07 | Not Started | Pending | Not Registered | Unpaid
LND-0431 | PRJ-KA-04 | Karnataka | Koppal | Kushtagi | Guttal | 572/9 | Yankappa Gowda | 3.95 | MOU Signed | Disputed | Not Registered | Partially Paid
LND-0490 | PRJ-KA-02 | Karnataka | Vijayapura | Muddebihal | Muddebihal | Gut No. 546/8 | Mahantappa Doddamani | 2.36 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0423 | PRJ-KA-01 | Karnataka | Gadag | Ron | Kanaginahal | 257/1 | Devendrappa Hosamani | 3.02 | Agreement Executed | Cleared | Not Registered | Fully Paid
LND-0047 | PRJ-MH-05 | Maharashtra | Latur | Ausa | Ausa | Gut No. 345/7 | Shriram More | 4.28 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0388 | PRJ-KA-02 | Karnataka | Bidar | Humnabad | Nilanga | Gut No. 356/5 | Revanasiddappa Gudadinni | 4.83 | Agreement Executed | Disputed | Not Registered | Fully Paid
LND-0096 | PRJ-MH-01 | Maharashtra | Osmanabad | Osmanabad | Kalamb | 71/9 | Ganpat Sawant | 1.47 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0414 | PRJ-KA-03 | Karnataka | Kalaburagi | Yadgir | Yadgir | Gut No. 633/8 | Eranna Gudadinni | 2.71 | MOU Signed | In Progress | Not Registered | Advance Paid
LND-0072 | PRJ-MH-01 | Maharashtra | Latur | Latur | Murud | Gut No. 332/2 | Kisan Bhosale | 4.39 | Not Started | Pending | Not Registered | Unpaid
LND-0207 | PRJ-MH-06 | Maharashtra | Pune | Haveli | Lonikand | Gut No. 503/4 | Narayan Chavan | 4.74 | Agreement Executed | Cleared | Registered | Partially Paid
LND-0326 | PRJ-KA-03 | Karnataka | Bidar | Bidar | Udgir | 966/3 | Veeranna Kamble | 4.6 | Agreement Executed | Disputed | Not Registered | Fully Paid
LND-0287 | PRJ-KA-06 | Karnataka | Bidar | Basavakalyan | Basavakalyan | Gut No. 844/8 | Nagappa Gowda | 0.62 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0278 | PRJ-KA-03 | Karnataka | Vijayapura | Vijayapura | Vijayapura | 601/3 | Nagaraj Gowda | 4.31 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0215 | PRJ-MH-04 | Maharashtra | Latur | Ausa | Nilanga | Gut No. 992/6 | Popat Londhe | 3.63 | Agreement Executed | Cleared | Registered | Fully Paid | 2023-07-29
LND-0462 | PRJ-KA-02 | Karnataka | Gadag | Gadag | Betgeri | 403/7 | Gurusiddappa Hosamani | 0.61 | Agreement Executed | Cleared | Registered | Partially Paid
LND-0145 | PRJ-MH-05 | Maharashtra | Osmanabad | Lohara | Washi | 627/5 | Laxman Sutar | 1.4 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0258 | PRJ-MH-01 | Maharashtra | Solapur | Mohol | Karkamb | 977/7 | Dnyandev Dhole | 4.4 | MOU Signed | Cleared | Not Registered | Advance Paid
LND-0097 | PRJ-MH-01 | Maharashtra | Osmanabad | Osmanabad | Kalamb | Gut No. 818/3 | Vitthal Kadam | 4.4 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0002 | PRJ-MH-07 | Maharashtra | Pune | Baramati | Pargaon | 239/9 | Balasaheb Patil | 3.03 | Agreement Executed | Cleared | Registered | Fully Paid | 2022-01-14
LND-0091 | PRJ-MH-01 | Maharashtra | Osmanabad | Lohara | Lohara | Gut No. 378/5 | Pramod Bhosale | 4.2 | MOU Signed | In Progress | Not Registered | Advance Paid
LND-0317 | PRJ-KA-07 | Karnataka | Gadag | Ron | Parasgad | 609/1 | Santosh Gowda | 3.44 | Not Started | Pending | Not Registered | Unpaid
LND-0282 | PRJ-KA-08 | Karnataka | Bidar | Basavakalyan | Kamalnagar | 710/2 | Lingappa Swamy | 4.04 | Not Started | Pending | Not Registered | Unpaid
LND-0080 | PRJ-MH-02 | Maharashtra | Nanded | Hadgaon | Hadgaon | 420/3 | Dnyandev Sutar | 4.02 | MOU Signed | Cleared | Not Registered | Partially Paid
LND-0307 | PRJ-KA-08 | Karnataka | Gadag | Ron | Parasgad | Gut No. 866/3 | Santosh Bennur | 1.32 | Not Started | Pending | Not Registered | Unpaid
LND-0234 | PRJ-MH-07 | Maharashtra | Solapur | Akkalkot | Nandeshwar | 834/4 | Tukaram Shinde | 3.07 | MOU Signed | Disputed | Not Registered | Advance Paid
LND-0119 | PRJ-MH-07 | Maharashtra | Latur | Chakur | Salegaon | 461/4 | Bhagwan Yadav | 2.64 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0033 | PRJ-MH-06 | Maharashtra | Osmanabad | Osmanabad | Kalamb | 676/4 | Dattatray Salve | 1.75 | Not Started | Pending | Not Registered | Unpaid
LND-0381 | PRJ-KA-03 | Karnataka | Raichur | Manvi | Kavital | Gut No. 268/9 | Yankappa Doddamani | 2.15 | MOU Signed | Disputed | Not Registered | Partially Paid
LND-0167 | PRJ-MH-08 | Maharashtra | Solapur | Mohol | Akluj | Gut No. 231/5 | Kisan Pawar | 3.67 | Agreement Executed | Disputed | Registered | Fully Paid | 2023-07-15
LND-0059 | PRJ-MH-05 | Maharashtra | Osmanabad | Osmanabad | Osmanabad | 324/2 | Shriram Chavan | 4.78 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0407 | PRJ-KA-03 | Karnataka | Bidar | Humnabad | Saidapur | Gut No. 235/4 | Srinivas Rao | 2.49 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0159 | PRJ-MH-07 | Maharashtra | Osmanabad | Osmanabad | Rui | 584/9 | Ganpat Waghmare | 2.99 | Not Started | Pending | Not Registered | Unpaid
LND-0264 | PRJ-MH-06 | Maharashtra | Latur | Ausa | Nilanga | 967/4 | Shankar Sawant | 0.99 | Not Started | Pending | Not Registered | Unpaid
LND-0089 | PRJ-MH-06 | Maharashtra | Latur | Latur | Udgir | 806/9 | Narayan Naik | 2.76 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0185 | PRJ-MH-07 | Maharashtra | Pune | Haveli | Manjari | 670/6 | Vitthal More | 4.97 | Agreement Executed | Cleared | Not Registered | Partially Paid
LND-0082 | PRJ-MH-05 | Maharashtra | Solapur | Akkalkot | Akkalkot | Gut No. 101/2 | Arjun More | 3.62 | Not Started | Pending | Not Registered | Unpaid
LND-0328 | PRJ-KA-05 | Karnataka | Gadag | Ron | Ron | 979/6 | Ashok Hiremath | 3.6 | Not Started | Pending | Not Registered | Unpaid
LND-0020 | PRJ-MH-02 | Maharashtra | Solapur | Mohol | Pandharpur | Gut No. 493/4 | Raju Bhosale | 4.56 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0251 | PRJ-MH-05 | Maharashtra | Pune | Haveli | Koregaon Bhima | 550/6 | Dattatray Sawant | 3.35 | Not Started | Pending | Not Registered | Unpaid
LND-0392 | PRJ-KA-04 | Karnataka | Vijayapura | Vijayapura | Indi | Gut No. 78/9 | Siddappa Biradar | 1.91 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0066 | PRJ-MH-05 | Maharashtra | Osmanabad | Lohara | Washi | 704/4 | Santosh Wagh | 3.15 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0081 | PRJ-MH-02 | Maharashtra | Osmanabad | Lohara | Bhoom | Gut No. 978/6 | Ashok Murkute | 4.49 | Agreement Executed | Cleared | Not Registered | Partially Paid
LND-0188 | PRJ-MH-07 | Maharashtra | Latur | Latur | Jalkot | 773/1 | Shankar Naik | 4.97 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0110 | PRJ-MH-06 | Maharashtra | Latur | Latur | Murud | Gut No. 540/5 | Suresh Gaikwad | 2.28 | Not Started | Pending | Not Registered | Unpaid
LND-0410 | PRJ-KA-08 | Karnataka | Vijayapura | Sindgi | Talikot | Gut No. 160/5 | Basavaraj Patil | 2.85 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0163 | PRJ-MH-05 | Maharashtra | Latur | Latur | Murud | Gut No. 690/2 | Mahadev Sawant | 1.88 | Not Started | Pending | Not Registered | Unpaid
LND-0311 | PRJ-KA-06 | Karnataka | Raichur | Manvi | Hatti | 324/3 | Nagaraj Naik | 2.69 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0416 | PRJ-KA-01 | Karnataka | Raichur | Raichur | Sindhanur | Gut No. 320/8 | Lingappa Hosamani | 3.64 | Not Started | Pending | Not Registered | Unpaid
LND-0412 | PRJ-KA-04 | Karnataka | Raichur | Manvi | Hatti | Gut No. 256/3 | Ramesh Honnalli | 2.25 | Agreement Executed | Cleared | Registered | Partially Paid
LND-0396 | PRJ-KA-08 | Karnataka | Bidar | Humnabad | Gadlegaon | Gut No. 324/1 | Basavaraj Nayak | 2.21 | Not Started | Pending | Not Registered | Unpaid
LND-0367 | PRJ-KA-03 | Karnataka | Kalaburagi | Sedam | Kamalapur | 754/8 | Lingappa Reddy | 1.48 | Agreement Executed | Cleared | Not Registered | Fully Paid
LND-0114 | PRJ-MH-07 | Maharashtra | Pune | Indapur | Nimgaon Ketki | Gut No. 852/6 | Dnyandev Thorat | 4.3 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0253 | PRJ-MH-05 | Maharashtra | Solapur | Mohol | Mohol | 719/1 | Pandhari Sutar | 4.79 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0218 | PRJ-MH-03 | Maharashtra | Latur | Ausa | Ausa | Gut No. 613/8 | Pramod Bhosale | 2.9 | Agreement Executed | Cleared | Registered | Partially Paid
LND-0480 | PRJ-KA-08 | Karnataka | Gadag | Ron | Kanaginahal | 788/2 | Ashok Kulkarni | 1.42 | Not Started | Pending | Not Registered | Unpaid
LND-0447 | PRJ-KA-03 | Karnataka | Gadag | Gadag | Ron | 262/3 | Shivanand Rao | 1.4 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0394 | PRJ-KA-02 | Karnataka | Bidar | Bidar | Udgir | Gut No. 629/1 | Nagaraj Bennur | 4.81 | Agreement Executed | Disputed | Registered | Fully Paid | 2023-07-17
LND-0433 | PRJ-KA-07 | Karnataka | Gadag | Ron | Kanaginahal | 577/9 | Nagappa Lamani | 3.95 | MOU Signed | Cleared | Not Registered | Partially Paid
LND-0061 | PRJ-MH-05 | Maharashtra | Pune | Baramati | Undewadi | 654/8 | Vitthal Patil | 3.08 | Agreement Executed | Disputed | Registered | Fully Paid | 2023-01-13
LND-0158 | PRJ-MH-01 | Maharashtra | Pune | Indapur | Bhandgaon | Gut No. 293/9 | Ramesh Deshmukh | 2.44 | MOU Signed | Disputed | Not Registered | Partially Paid
LND-0336 | PRJ-KA-06 | Karnataka | Bidar | Basavakalyan | Basavakalyan | 791/8 | Channappa Doddamani | 4.8 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0342 | PRJ-KA-01 | Karnataka | Raichur | Raichur | Raichur | 205/5 | Nagaraj Desai | 4.93 | MOU Signed | In Progress | Not Registered | Advance Paid
LND-0322 | PRJ-KA-01 | Karnataka | Gadag | Gadag | Gadag | Gut No. 153/2 | Nagaraj Hiremath | 0.84 | Not Started | Pending | Not Registered | Unpaid
LND-0084 | PRJ-MH-02 | Maharashtra | Nanded | Hadgaon | Umri | 510/3 | Rajendra Dhole | 3.37 | Agreement Executed | Disputed | Not Registered | Fully Paid
LND-0214 | PRJ-MH-07 | Maharashtra | Osmanabad | Lohara | Washi | Gut No. 451/6 | Mahadev Wagh | 4.88 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0295 | PRJ-KA-02 | Karnataka | Koppal | Koppal | Kushtagi | Gut No. 899/7 | Eranna Lamani | 3.45 | Agreement Executed | Cleared | Not Registered | Fully Paid
LND-0492 | PRJ-KA-08 | Karnataka | Bidar | Humnabad | Gadlegaon | Gut No. 334/9 | Veeranna Hosamani | 1.29 | Agreement Executed | Cleared | Not Registered | Fully Paid
LND-0003 | PRJ-MH-03 | Maharashtra | Latur | Ausa | Ahmedpur | 221/6 | Vitthal Jadhav | 2.21 | MOU Signed | Cleared | Not Registered | Partially Paid
LND-0438 | PRJ-KA-05 | Karnataka | Bidar | Humnabad | Gadlegaon | Gut No. 81/1 | Nagaraj Hugar | 2.07 | Agreement Executed | Disputed | Not Registered | Partially Paid
LND-0453 | PRJ-KA-04 | Karnataka | Gadag | Gadag | Shirhatti | 884/3 | Fakeerappa Hiremath | 4.59 | Agreement Executed | Cleared | Not Registered | Fully Paid
LND-0331 | PRJ-KA-05 | Karnataka | Bidar | Humnabad | Kamalanagar | Gut No. 413/4 | Mallappa Hosamani | 2.5 | Agreement Executed | Cleared | Registered | Fully Paid | 2023-10-10
LND-0098 | PRJ-MH-04 | Maharashtra | Nanded | Hadgaon | Hadgaon | 272/1 | Shankar Londhe | 2.39 | Not Started | Pending | Not Registered | Unpaid
LND-0106 | PRJ-MH-07 | Maharashtra | Nanded | Biloli | Mukhed | Gut No. 30/3 | Santosh Murkute | 3.93 | MOU Signed | Cleared | Not Registered | Advance Paid
LND-0191 | PRJ-MH-04 | Maharashtra | Osmanabad | Lohara | Anatpal | Gut No. 937/1 | Vilas Thorat | 4.86 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0285 | PRJ-KA-02 | Karnataka | Koppal | Koppal | Kushtagi | Gut No. 722/1 | Yankappa Honnalli | 1.24 | Agreement Executed | Cleared | Not Registered | Partially Paid
LND-0293 | PRJ-KA-07 | Karnataka | Kalaburagi | Sedam | Malkhed | Gut No. 328/2 | Mallappa Lamani | 3 | MOU Signed | Cleared | Not Registered | Partially Paid
LND-0204 | PRJ-MH-04 | Maharashtra | Solapur | Akkalkot | Wadwal Nagnath | Gut No. 278/1 | Dnyandev Kadam | 4.67 | Not Started | Pending | Not Registered | Unpaid
LND-0071 | PRJ-MH-06 | Maharashtra | Latur | Ausa | Ahmedpur | 879/3 | Bhagwan Thorat | 3.62 | MOU Signed | Disputed | Not Registered | Partially Paid
LND-0425 | PRJ-KA-08 | Karnataka | Bidar | Humnabad | Gadlegaon | Gut No. 752/3 | Basavaraj Gudadinni | 4.36 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0321 | PRJ-KA-05 | Karnataka | Kalaburagi | Kalaburagi | Chitapur | Gut No. 933/4 | Ramesh Biradar | 1.99 | Not Started | Pending | Not Registered | Unpaid
LND-0312 | PRJ-KA-01 | Karnataka | Raichur | Sindhanur | Maski | 591/3 | Devendrappa Naik | 1.08 | Agreement Executed | Disputed | Registered | Fully Paid | 2024-09-04
LND-0262 | PRJ-MH-03 | Maharashtra | Osmanabad | Osmanabad | Osmanabad | 919/9 | Mahadev Murkute | 4.53 | Agreement Executed | Cleared | Not Registered | Partially Paid
LND-0184 | PRJ-MH-01 | Maharashtra | Pune | Indapur | Indapur | Gut No. 419/3 | Kisan Kulkarni | 3.95 | Agreement Executed | Disputed | Registered | Fully Paid | 2024-02-13
LND-0102 | PRJ-MH-04 | Maharashtra | Latur | Ausa | Nilanga | Gut No. 348/8 | Dattatray Thorat | 3.78 | MOU Signed | Cleared | Not Registered | Partially Paid
LND-0335 | PRJ-KA-01 | Karnataka | Kalaburagi | Yadgir | Shorapur | Gut No. 110/5 | Anil Nayak | 1.34 | Agreement Executed | Cleared | Registered | Partially Paid
LND-0419 | PRJ-KA-04 | Karnataka | Raichur | Sindhanur | Mudgal | Gut No. 163/1 | Srinivas Bennur | 2.84 | MOU Signed | Cleared | Not Registered | Partially Paid
LND-0023 | PRJ-MH-03 | Maharashtra | Pune | Haveli | Uruli Kanchan | 414/2 | Pramod Gaikwad | 3.11 | Not Started | Pending | Not Registered | Unpaid
LND-0209 | PRJ-MH-06 | Maharashtra | Pune | Baramati | Malegaon | Gut No. 456/6 | Kisan Mane | 0.96 | Not Started | Pending | Not Registered | Unpaid
LND-0319 | PRJ-KA-05 | Karnataka | Raichur | Manvi | Manvi | Gut No. 638/3 | Yankappa Gowda | 2.8 | Not Started | Pending | Not Registered | Unpaid
LND-0448 | PRJ-KA-01 | Karnataka | Bidar | Basavakalyan | Hulsoor | Gut No. 886/2 | Basavaraj Rao | 4.4 | Agreement Executed | Cleared | Registered | Partially Paid
LND-0224 | PRJ-MH-08 | Maharashtra | Solapur | Barshi | Shegaon | 656/7 | Dattatray Patil | 3.82 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0401 | PRJ-KA-07 | Karnataka | Bidar | Humnabad | Kamalanagar | 221/5 | Devendrappa Honnalli | 0.93 | MOU Signed | Cleared | Not Registered | Partially Paid
LND-0070 | PRJ-MH-05 | Maharashtra | Nanded | Biloli | Deglur | Gut No. 532/8 | Santosh More | 4.99 | Agreement Executed | Disputed | Not Registered | Fully Paid
LND-0454 | PRJ-KA-02 | Karnataka | Koppal | Kushtagi | Kushtagi | 326/3 | Srinivas Patil | 3.94 | Agreement Executed | Disputed | Registered | Fully Paid | 2023-07-15
LND-0194 | PRJ-MH-04 | Maharashtra | Solapur | Akkalkot | Akkalkot | Gut No. 937/4 | Laxman Yadav | 3.67 | Agreement Executed | Cleared | Registered | Fully Paid | 2024-02-19
LND-0016 | PRJ-MH-02 | Maharashtra | Pune | Baramati | Pargaon | 881/6 | Dnyandev Naik | 1.57 | Agreement Executed | Cleared | Not Registered | Fully Paid
LND-0042 | PRJ-MH-01 | Maharashtra | Nanded | Biloli | Biloli | Gut No. 137/8 | Subhash Naik | 4.95 | MOU Signed | Cleared | Not Registered | Partially Paid
LND-0497 | PRJ-KA-07 | Karnataka | Koppal | Koppal | Gangavathi | Gut No. 143/4 | Suresh Lamani | 4.29 | MOU Signed | Cleared | Not Registered | Advance Paid
LND-0397 | PRJ-KA-06 | Karnataka | Vijayapura | Muddebihal | Devara Hippargi | 562/5 | Revanasiddappa Swamy | 2.62 | MOU Signed | Cleared | Not Registered | Advance Paid
LND-0292 | PRJ-KA-03 | Karnataka | Bidar | Basavakalyan | Kamalnagar | 996/4 | Nagappa Kulkarni | 0.69 | Not Started | Pending | Not Registered | Unpaid
LND-0203 | PRJ-MH-01 | Maharashtra | Solapur | Mohol | Pandharpur | Gut No. 661/6 | Pramod Deshmukh | 4.53 | Not Started | Pending | Not Registered | Unpaid
LND-0426 | PRJ-KA-07 | Karnataka | Kalaburagi | Sedam | Sannati | 628/5 | Gurusiddappa Kamble | 3.38 | Not Started | Pending | Not Registered | Unpaid
LND-0387 | PRJ-KA-03 | Karnataka | Bidar | Basavakalyan | Udgir | Gut No. 686/7 | Mahantappa Doddamani | 1.4 | Not Started | Pending | Not Registered | Unpaid
LND-0231 | PRJ-MH-03 | Maharashtra | Pune | Haveli | Uruli Kanchan | 300/1 | Santosh Gaikwad | 2.92 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0026 | PRJ-MH-04 | Maharashtra | Nanded | Hadgaon | Kinwat | Gut No. 903/2 | Rajendra Waghmare | 1.78 | Agreement Executed | Disputed | Not Registered | Fully Paid
LND-0157 | PRJ-MH-08 | Maharashtra | Nanded | Hadgaon | Bhokar | Gut No. 510/1 | Dnyandev Bhosale | 2.77 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0225 | PRJ-MH-07 | Maharashtra | Pune | Haveli | Koregaon Bhima | 286/2 | Pramod Deshmukh | 4.1 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0029 | PRJ-MH-03 | Maharashtra | Latur | Chakur | Kinhala | 115/2 | Laxman Kulkarni | 2.96 | MOU Signed | Disputed | Not Registered | Advance Paid
LND-0127 | PRJ-MH-08 | Maharashtra | Solapur | Barshi | Bhalwani | Gut No. 473/5 | Kisan Bhosale | 2.76 | Agreement Executed | Cleared | Not Registered | Partially Paid
LND-0370 | PRJ-KA-05 | Karnataka | Raichur | Raichur | Lingsugur | Gut No. 362/6 | Devendrappa Biradar | 4.49 | Not Started | Pending | Not Registered | Unpaid
LND-0228 | PRJ-MH-04 | Maharashtra | Osmanabad | Osmanabad | Kalamb | Gut No. 711/3 | Anil Bhosale | 2.38 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0064 | PRJ-MH-08 | Maharashtra | Osmanabad | Lohara | Washi | Gut No. 583/1 | Balasaheb Londhe | 0.95 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0153 | PRJ-MH-08 | Maharashtra | Nanded | Hadgaon | Mahur | Gut No. 251/7 | Popat Dhole | 0.83 | Not Started | Pending | Not Registered | Unpaid
LND-0422 | PRJ-KA-01 | Karnataka | Vijayapura | Muddebihal | Shirahatti | 129/8 | Revanasiddappa Hugar | 4.92 | MOU Signed | Cleared | Not Registered | Advance Paid
LND-0406 | PRJ-KA-04 | Karnataka | Kalaburagi | Yadgir | Yadgir | 66/8 | Suresh Reddy | 0.62 | Agreement Executed | Cleared | Not Registered | Fully Paid
LND-0105 | PRJ-MH-02 | Maharashtra | Nanded | Biloli | Deglur | Gut No. 230/2 | Narayan Chavan | 2.15 | MOU Signed | Disputed | Not Registered | Advance Paid
LND-0009 | PRJ-MH-03 | Maharashtra | Nanded | Hadgaon | Hadgaon | 882/2 | Shankar Wagh | 1.22 | Agreement Executed | Cleared | Registered | Fully Paid | 2024-08-16
LND-0076 | PRJ-MH-07 | Maharashtra | Latur | Ausa | Nilanga | Gut No. 565/3 | Dattatray Kale | 4.65 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0107 | PRJ-MH-03 | Maharashtra | Solapur | Akkalkot | Khanderajuri | 146/1 | Dnyandev Londhe | 2.89 | Agreement Executed | Disputed | Registered | Fully Paid | 2022-11-19
LND-0174 | PRJ-MH-05 | Maharashtra | Nanded | Biloli | Kandhar | Gut No. 466/9 | Anil Sutar | 4.5 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0500 | PRJ-KA-03 | Karnataka | Raichur | Manvi | Manvi | Gut No. 868/4 | Ramesh Hiremath | 1.71 | MOU Signed | In Progress | Not Registered | Advance Paid
LND-0117 | PRJ-MH-03 | Maharashtra | Latur | Ausa | Chakur | Gut No. 698/6 | Raju Wagh | 1.92 | Agreement Executed | Cleared | Registered | Fully Paid | 2023-09-13
LND-0025 | PRJ-MH-03 | Maharashtra | Osmanabad | Tuljapur | Murud | 2026-10-08 | Balasaheb Sawant | 4.98 | Not Started | Pending | Not Registered | Unpaid
LND-0463 | PRJ-KA-05 | Karnataka | Vijayapura | Muddebihal | Shirahatti | 94/2 | Ramesh Hosamani | 3.35 | Not Started | Pending | Not Registered | Unpaid
LND-0304 | PRJ-KA-01 | Karnataka | Koppal | Kushtagi | Bettadur | Gut No. 306/2 | Devendrappa Naik | 2.01 | MOU Signed | Disputed | Not Registered | Partially Paid
LND-0495 | PRJ-KA-02 | Karnataka | Koppal | Koppal | Kanakagiri | Gut No. 868/3 | Fakeerappa Reddy | 2.16 | Not Started | Pending | Not Registered | Unpaid
LND-0004 | PRJ-MH-01 | Maharashtra | Latur | Chakur | Chakur | Gut No. 81/9 | Popat Wagh | 3.28 | MOU Signed | Disputed | Not Registered | Advance Paid
LND-0034 | PRJ-MH-05 | Maharashtra | Osmanabad | Lohara | Bhoom | Gut No. 696/9 | Bhagwan Patil | 1.02 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0330 | PRJ-KA-01 | Karnataka | Gadag | Gadag | Shirhatti | Gut No. 873/8 | Siddappa Naik | 3.88 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0012 | PRJ-MH-05 | Maharashtra | Nanded | Biloli | Deglur | Gut No. 781/3 | Vilas Naik | 4.63 | MOU Signed | Cleared | Not Registered | Advance Paid
LND-0393 | PRJ-KA-04 | Karnataka | Raichur | Manvi | Turvihal | 754/4 | Eranna Nayak | 1.53 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0439 | PRJ-KA-01 | Karnataka | Gadag | Ron | Ron | Gut No. 537/1 | Gurusiddappa Bennur | 3.04 | MOU Signed | Disputed | Not Registered | Advance Paid
LND-0355 | PRJ-KA-06 | Karnataka | Bidar | Basavakalyan | Basavakalyan | 657/2 | Nagaraj Doddamani | 0.7 | Not Started | Pending | Not Registered | Unpaid
LND-0037 | PRJ-MH-02 | Maharashtra | Osmanabad | Lohara | Omerga | 738/5 | Anil Pawar | 3.5 | MOU Signed | Cleared | Not Registered | Partially Paid
LND-0362 | PRJ-KA-06 | Karnataka | Koppal | Kushtagi | Bettadur | 580/6 | Gurusiddappa Kamble | 1.26 | MOU Signed | In Progress | Not Registered | Advance Paid
LND-0383 | PRJ-KA-07 | Karnataka | Gadag | Gadag | Mundargi | 766/4 | Channappa Desai | 0.95 | Agreement Executed | Disputed | Not Registered | Partially Paid
LND-0368 | PRJ-KA-06 | Karnataka | Kalaburagi | Kalaburagi | Yadgir | 531/6 | Mahantappa Biradar | 4.63 | Not Started | Pending | Not Registered | Unpaid
LND-0236 | PRJ-MH-03 | Maharashtra | Solapur | Mohol | Velapur | Gut No. 849/4 | Kisan Kadam | 2.27 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0206 | PRJ-MH-07 | Maharashtra | Solapur | Akkalkot | Akkalkot | Gut No. 55/2 | Mahadev Gaikwad | 4.27 | MOU Signed | Disputed | Not Registered | Partially Paid
LND-0192 | PRJ-MH-05 | Maharashtra | Solapur | Barshi | Barshi | Gut No. 868/6 | Dnyandev Chavan | 3.76 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0395 | PRJ-KA-08 | Karnataka | Kalaburagi | Sedam | Devara Hippargi | Gut No. 228/3 | Shivanand Hiremath | 4.1 | Agreement Executed | Cleared | Registered | Fully Paid | 2022-12-24
LND-0260 | PRJ-MH-04 | Maharashtra | Nanded | Biloli | Deglur | 955/7 | Ramesh Gaikwad | 2.94 | Not Started | Pending | Not Registered | Unpaid
LND-0275 | PRJ-KA-04 | Karnataka | Koppal | Gangavathi | Hospet | 181/4 | Rajesh Hugar | 4.13 | MOU Signed | Disputed | Not Registered | Advance Paid
LND-0468 | PRJ-KA-03 | Karnataka | Bidar | Humnabad | Gadlegaon | Gut No. 340/2 | Shivanand Gowda | 2.38 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0186 | PRJ-MH-01 | Maharashtra | Osmanabad | Tuljapur | Umarga | Gut No. 545/7 | Sopan Gaikwad | 1.61 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0154 | PRJ-MH-03 | Maharashtra | Latur | Ausa | Deoni | Gut No. 209/6 | Balasaheb Kulkarni | 1.91 | MOU Signed | Disputed | Not Registered | Partially Paid
LND-0315 | PRJ-KA-05 | Karnataka | Vijayapura | Sindgi | Kolhar | Gut No. 445/3 | Gurusiddappa Biradar | 2.12 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0430 | PRJ-KA-01 | Karnataka | Gadag | Gadag | Nargund | 968/4 | Ashok Gowda | 0.96 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0169 | PRJ-MH-05 | Maharashtra | Pune | Indapur | Bhandgaon | Gut No. 766/8 | Ganpat Kale | 4.23 | MOU Signed | Disputed | Not Registered | Partially Paid
LND-0499 | PRJ-KA-07 | Karnataka | Raichur | Manvi | Kavital | Gut No. 639/3 | Channappa Hiremath | 2.41 | Agreement Executed | Disputed | Registered | Partially Paid
LND-0116 | PRJ-MH-03 | Maharashtra | Solapur | Mohol | Sangola | Gut No. 203/3 | Balasaheb Kulkarni | 3.92 | Not Started | Pending | Not Registered | Unpaid
LND-0358 | PRJ-KA-01 | Karnataka | Koppal | Kushtagi | Guttal | 43/1 | Rajesh Gudadinni | 2.27 | Not Started | Pending | Not Registered | Unpaid
LND-0246 | PRJ-MH-03 | Maharashtra | Pune | Haveli | Wagholi | Gut No. 987/7 | Bhagwan Kulkarni | 1.62 | Not Started | Pending | Not Registered | Unpaid
LND-0486 | PRJ-KA-02 | Karnataka | Raichur | Sindhanur | Maski | Gut No. 632/6 | Fakeerappa Hugar | 4.18 | Not Started | Pending | Not Registered | Unpaid
LND-0449 | PRJ-KA-06 | Karnataka | Raichur | Manvi | Kavital | 191/4 | Ashok Hosamani | 3.02 | Not Started | Pending | Not Registered | Unpaid
LND-0389 | PRJ-KA-03 | Karnataka | Raichur | Manvi | Manvi | 516/5 | Gurusiddappa Gowda | 4.11 | MOU Signed | Disputed | Not Registered | Partially Paid
LND-0235 | PRJ-MH-06 | Maharashtra | Osmanabad | Tuljapur | Umarga | Gut No. 976/9 | Subhash Deshmukh | 1.11 | Agreement Executed | Cleared | Registered | Partially Paid
LND-0390 | PRJ-KA-08 | Karnataka | Raichur | Manvi | Hatti | 776/6 | Nagaraj Hosamani | 3.57 | Not Started | Pending | Not Registered | Unpaid
LND-0299 | PRJ-KA-07 | Karnataka | Kalaburagi | Sedam | Kamalapur | 178/4 | Nagappa Reddy | 1.62 | Agreement Executed | Cleared | Registered | Partially Paid
LND-0152 | PRJ-MH-01 | Maharashtra | Pune | Baramati | Malegaon | Gut No. 667/4 | Kisan Sawant | 2.37 | Not Started | Pending | Not Registered | Unpaid
LND-0411 | PRJ-KA-08 | Karnataka | Koppal | Koppal | Yelburga | Gut No. 307/1 | Nagaraj Kamble | 4.09 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0470 | PRJ-KA-05 | Karnataka | Raichur | Raichur | Raichur | Gut No. 338/9 | Yankappa Hiremath | 1.44 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0436 | PRJ-KA-08 | Karnataka | Vijayapura | Vijayapura | Basavana Bagewadi | Gut No. 376/4 | Revanasiddappa Swamy | 4.15 | Not Started | Pending | Not Registered | Unpaid
LND-0487 | PRJ-KA-08 | Karnataka | Koppal | Koppal | Koppal | Gut No. 100/8 | Fakeerappa Honnalli | 3.7 | Agreement Executed | Disputed | Not Registered | Partially Paid
LND-0183 | PRJ-MH-07 | Maharashtra | Osmanabad | Osmanabad | Naldurg | 593/2 | Suresh Thorat | 2.05 | Not Started | Pending | Not Registered | Unpaid
LND-0309 | PRJ-KA-06 | Karnataka | Vijayapura | Sindgi | Kolhar | Gut No. 475/2 | Devendrappa Reddy | 4.4 | Not Started | Pending | Not Registered | Unpaid
LND-0178 | PRJ-MH-05 | Maharashtra | Osmanabad | Lohara | Anatpal | 684/2 | Arjun Pawar | 1.22 | MOU Signed | Disputed | Not Registered | Advance Paid
LND-0344 | PRJ-KA-05 | Karnataka | Gadag | Gadag | Ron | Gut No. 427/6 | Suresh Reddy | 0.56 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0125 | PRJ-MH-01 | Maharashtra | Osmanabad | Lohara | Anatpal | Gut No. 158/3 | Pandhari Murkute | 3.97 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0364 | PRJ-KA-03 | Karnataka | Gadag | Gadag | Nargund | 913/9 | Nagappa Swamy | 3.8 | Not Started | Pending | Not Registered | Unpaid
LND-0382 | PRJ-KA-04 | Karnataka | Raichur | Manvi | Kavital | Gut No. 184/6 | Suresh Bennur | 2.68 | MOU Signed | Disputed | Not Registered | Partially Paid
LND-0250 | PRJ-MH-01 | Maharashtra | Latur | Chakur | Yednapur | Gut No. 434/7 | Dnyandev Wagh | 2.91 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0371 | PRJ-KA-03 | Karnataka | Raichur | Raichur | Manvi | 527/5 | Nagappa Kulkarni | 1.34 | MOU Signed | Disputed | Not Registered | Advance Paid
LND-0365 | PRJ-KA-02 | Karnataka | Bidar | Humnabad | Humnabad | Gut No. 788/4 | Shivanand Bennur | 1.67 | Agreement Executed | Cleared | Registered | Fully Paid | 2023-04-03
LND-0179 | PRJ-MH-05 | Maharashtra | Osmanabad | Lohara | Anatpal | 981/3 | Sanjay Kulkarni | 2.55 | MOU Signed | Cleared | Not Registered | Partially Paid
LND-0077 | PRJ-MH-07 | Maharashtra | Osmanabad | Lohara | Omerga | 290/5 | Sopan Sawant | 3.11 | Agreement Executed | Cleared | Registered | Fully Paid | 2023-12-08
LND-0049 | PRJ-MH-06 | Maharashtra | Osmanabad | Tuljapur | Murud | Gut No. 259/2 | Sanjay Patil | 3.87 | Not Started | Pending | Not Registered | Unpaid
LND-0450 | PRJ-KA-01 | Karnataka | Kalaburagi | Sedam | Devara Hippargi | Gut No. 502/7 | Srinivas Desai | 0.58 | MOU Signed | Cleared | Not Registered | Partially Paid
LND-0213 | PRJ-MH-06 | Maharashtra | Osmanabad | Osmanabad | Naldurg | Gut No. 609/4 | Arjun Deshmukh | 1.11 | Not Started | Pending | Not Registered | Unpaid
LND-0011 | PRJ-MH-07 | Maharashtra | Solapur | Barshi | Barshi | Gut No. 996/9 | Kisan More | 2.78 | Not Started | Pending | Not Registered | Unpaid
LND-0280 | PRJ-KA-04 | Karnataka | Gadag | Gadag | Ron | Gut No. 752/5 | Hanumantha Desai | 3.78 | Agreement Executed | Cleared | Not Registered | Fully Paid
LND-0476 | PRJ-KA-08 | Karnataka | Raichur | Manvi | Manvi | Gut No. 579/6 | Suresh Bennur | 0.58 | MOU Signed | Cleared | Not Registered | Advance Paid
LND-0052 | PRJ-MH-03 | Maharashtra | Osmanabad | Osmanabad | Shirur Anantpal | 952/5 | Pramod Kadam | 4.59 | Agreement Executed | Disputed | Not Registered | Partially Paid
LND-0417 | PRJ-KA-06 | Karnataka | Bidar | Bidar | Bidar | Gut No. 795/7 | Mallappa Bennur | 2.62 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0353 | PRJ-KA-02 | Karnataka | Kalaburagi | Sedam | Sannati | 765/3 | Basavaraj Hosamani | 3.73 | Not Started | Pending | Not Registered | Unpaid
LND-0118 | PRJ-MH-05 | Maharashtra | Nanded | Biloli | Kandhar | 318/8 | Arjun Shinde | 0.76 | MOU Signed | In Progress | Not Registered | Advance Paid
LND-0021 | PRJ-MH-07 | Maharashtra | Osmanabad | Tuljapur | Murud | Gut No. 714/9 | Subhash Murkute | 2.69 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0088 | PRJ-MH-05 | Maharashtra | Solapur | Akkalkot | Akkalkot | 317/8 | Suresh Sawant | 2.14 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0333 | PRJ-KA-05 | Karnataka | Koppal | Kushtagi | Guttal | Gut No. 974/6 | Lingappa Reddy | 4.17 | Agreement Executed | Disputed | Registered | Fully Paid | 2024-07-15
LND-0094 | PRJ-MH-07 | Maharashtra | Pune | Indapur | Lonand | Gut No. 962/5 | Suresh Murkute | 2.17 | Agreement Executed | Disputed | Not Registered | Fully Paid
LND-0024 | PRJ-MH-02 | Maharashtra | Latur | Chakur | Salegaon | Gut No. 958/5 | Ganpat Kadam | 3.72 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0284 | PRJ-KA-03 | Karnataka | Raichur | Raichur | Raichur | Gut No. 21/6 | Eranna Gowda | 0.83 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0346 | PRJ-KA-03 | Karnataka | Kalaburagi | Sedam | Kamalapur | 387/1 | Yankappa Swamy | 3 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0015 | PRJ-MH-07 | Maharashtra | Osmanabad | Tuljapur | Umarga | Gut No. 124/4 | Rajendra Jadhav | 2.02 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0479 | PRJ-KA-03 | Karnataka | Bidar | Basavakalyan | Basavakalyan | 936/2 | Channappa Hiremath | 0.61 | Agreement Executed | Cleared | Not Registered | Fully Paid
LND-0400 | PRJ-KA-03 | Karnataka | Raichur | Sindhanur | Maski | Gut No. 805/8 | Fakeerappa Swamy | 3.03 | Not Started | Pending | Not Registered | Unpaid
LND-0175 | PRJ-MH-04 | Maharashtra | Pune | Indapur | Nimgaon Ketki | Gut No. 664/5 | Laxman More | 0.56 | MOU Signed | Cleared | Not Registered | Advance Paid
LND-0366 | PRJ-KA-05 | Karnataka | Kalaburagi | Yadgir | Wadagera | 407/6 | Ashok Patil | 3.48 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0266 | PRJ-MH-03 | Maharashtra | Osmanabad | Lohara | Bhoom | 221/6 | Shankar Jadhav | 3.7 | MOU Signed | Cleared | Not Registered | Advance Paid
LND-0138 | PRJ-MH-05 | Maharashtra | Nanded | Hadgaon | Umri | Gut No. 260/1 | Kisan Wagh | 1.36 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0308 | PRJ-KA-08 | Karnataka | Kalaburagi | Sedam | Devara Hippargi | 970/6 | Prakash Naik | 1.5 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0279 | PRJ-KA-07 | Karnataka | Koppal | Koppal | Kushtagi | Gut No. 331/3 | Siddappa Kamble | 4.06 | Agreement Executed | Disputed | Not Registered | Fully Paid
LND-0341 | PRJ-KA-06 | Karnataka | Koppal | Gangavathi | Hampi | Gut No. 691/9 | Fakeerappa Kamble | 4.14 | Not Started | Pending | Not Registered | Unpaid
LND-0220 | PRJ-MH-01 | Maharashtra | Pune | Indapur | Nimgaon Ketki | 457/6 | Dattatray Dhole | 3.98 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0210 | PRJ-MH-03 | Maharashtra | Latur | Ausa | Chakur | Gut No. 106/1 | Dnyandev Waghmare | 2.99 | MOU Signed | Cleared | Not Registered | Advance Paid
LND-0377 | PRJ-KA-08 | Karnataka | Koppal | Kushtagi | Kushtagi | 96/8 | Santosh Kulkarni | 4.56 | Not Started | Pending | Not Registered | Unpaid
LND-0441 | PRJ-KA-02 | Karnataka | Raichur | Manvi | Manvi | Gut No. 269/2 | Mahantappa Hiremath | 2.46 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0494 | PRJ-KA-05 | Karnataka | Raichur | Manvi | Kavital | Gut No. 201/4 | Santosh Hugar | 1.85 | MOU Signed | Cleared | Not Registered | Partially Paid
LND-0405 | PRJ-KA-07 | Karnataka | Vijayapura | Sindgi | Tikota | Gut No. 424/3 | Siddappa Patil | 1.06 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0427 | PRJ-KA-02 | Karnataka | Koppal | Kushtagi | Kushtagi | 856/3 | Siddappa Reddy | 1.41 | Agreement Executed | Cleared | Not Registered | Partially Paid
LND-0256 | PRJ-MH-02 | Maharashtra | Solapur | Akkalkot | Wadwal Nagnath | 46/1 | Rajendra Shinde | 2.62 | Agreement Executed | Cleared | Not Registered | Partially Paid
LND-0324 | PRJ-KA-05 | Karnataka | Vijayapura | Muddebihal | Devara Hippargi | Gut No. 757/2 | Veeranna Reddy | 0.54 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0208 | PRJ-MH-05 | Maharashtra | Solapur | Akkalkot | Akkalkot | 275/3 | Dattatray Murkute | 4.03 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0442 | PRJ-KA-04 | Karnataka | Raichur | Sindhanur | Gangavathi | 575/9 | Revanasiddappa Hegde | 0.82 | Agreement Executed | Disputed | Not Registered | Partially Paid
LND-0481 | PRJ-KA-08 | Karnataka | Raichur | Manvi | Kavital | 2026-05-05 | Shivanand Gudadinni | 4.42 | MOU Signed | Cleared | Not Registered | Advance Paid
LND-0217 | PRJ-MH-08 | Maharashtra | Solapur | Barshi | Natepute | 839/7 | Subhash Sutar | 1.13 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0104 | PRJ-MH-06 | Maharashtra | Solapur | Akkalkot | Akkalkot | Gut No. 687/2 | Mahadev Waghmare | 4.43 | Agreement Executed | Cleared | Registered | Fully Paid | 2023-12-22
LND-0261 | PRJ-MH-06 | Maharashtra | Pune | Haveli | Wagholi | Gut No. 107/4 | Anil Gaikwad | 2.39 | Not Started | Pending | Not Registered | Unpaid
LND-0123 | PRJ-MH-05 | Maharashtra | Nanded | Hadgaon | Mahur | 687/9 | Dnyandev Wagh | 3.52 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0475 | PRJ-KA-03 | Karnataka | Kalaburagi | Yadgir | Gurumitkal | Gut No. 939/8 | Shivanand Honnalli | 1.11 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0198 | PRJ-MH-06 | Maharashtra | Solapur | Mohol | Velapur | Gut No. 189/9 | Ashok Shinde | 2.86 | Not Started | Pending | Not Registered | Unpaid
LND-0471 | PRJ-KA-02 | Karnataka | Raichur | Manvi | Kavital | Gut No. 438/6 | Eranna Hiremath | 3.09 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0283 | PRJ-KA-01 | Karnataka | Raichur | Sindhanur | Kushtagi | 906/7 | Devendrappa Lamani | 2.08 | Agreement Executed | Cleared | Registered | Partially Paid
LND-0474 | PRJ-KA-05 | Karnataka | Vijayapura | Muddebihal | Horti | Gut No. 786/1 | Veeranna Hugar | 2.04 | Not Started | Pending | Not Registered | Unpaid
LND-0349 | PRJ-KA-02 | Karnataka | Vijayapura | Vijayapura | Basavana Bagewadi | Gut No. 340/6 | Fakeerappa Nayak | 4.78 | Agreement Executed | Cleared | Not Registered | Fully Paid
LND-0101 | PRJ-MH-05 | Maharashtra | Nanded | Hadgaon | Bhokar | Gut No. 465/9 | Balasaheb Thorat | 0.95 | Not Started | Pending | Not Registered | Unpaid
LND-0232 | PRJ-MH-02 | Maharashtra | Nanded | Biloli | Kandhar | Gut No. 556/1 | Kisan Londhe | 2.49 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0085 | PRJ-MH-05 | Maharashtra | Nanded | Biloli | Biloli | Gut No. 968/6 | Pramod Pawar | 3.38 | Agreement Executed | Disputed | Registered | Fully Paid | 2023-02-12
LND-0404 | PRJ-KA-07 | Karnataka | Gadag | Ron | Ron | 166/6 | Revanasiddappa Hugar | 1.93 | MOU Signed | Disputed | Not Registered | Partially Paid
LND-0245 | PRJ-MH-03 | Maharashtra | Latur | Ausa | Nilanga | 942/7 | Balasaheb Kadam | 2.49 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0069 | PRJ-MH-07 | Maharashtra | Osmanabad | Lohara | Omerga | 94/4 | Subhash Sawant | 3.14 | Not Started | Pending | Not Registered | Unpaid
LND-0467 | PRJ-KA-01 | Karnataka | Kalaburagi | Sedam | Devara Hippargi | 51/3 | Hanumantha Reddy | 3.44 | Not Started | Pending | Not Registered | Unpaid
LND-0276 | PRJ-KA-06 | Karnataka | Koppal | Kushtagi | Guttal | 857/8 | Suresh Rao | 1.29 | Not Started | Pending | Not Registered | Unpaid
LND-0010 | PRJ-MH-05 | Maharashtra | Nanded | Biloli | Naigaon | 699/9 | Kisan Mane | 3.96 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0482 | PRJ-KA-02 | Karnataka | Koppal | Kushtagi | Bettadur | 592/5 | Prakash Nayak | 1.94 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0001 | PRJ-MH-02 | Maharashtra | Pune | Haveli | Lonikand | 229/3 | Shriram Deshmukh | 3.55 | Not Started | Pending | Not Registered | Unpaid
LND-0164 | PRJ-MH-08 | Maharashtra | Osmanabad | Lohara | Bhoom | 739/1 | Pramod Sutar | 1.27 | Agreement Executed | Cleared | Not Registered | Partially Paid
LND-0168 | PRJ-MH-05 | Maharashtra | Pune | Haveli | Manjari | Gut No. 918/7 | Sopan Waghmare | 4.8 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0288 | PRJ-KA-08 | Karnataka | Bidar | Basavakalyan | Udgir | Gut No. 501/5 | Mallappa Honnalli | 2.95 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0128 | PRJ-MH-05 | Maharashtra | Pune | Haveli | Wagholi | Gut No. 568/2 | Laxman Naik | 4.33 | MOU Signed | In Progress | Not Registered | Advance Paid
LND-0348 | PRJ-KA-02 | Karnataka | Gadag | Ron | Parasgad | 980/3 | Ashok Naik | 4.04 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0318 | PRJ-KA-01 | Karnataka | Gadag | Gadag | Ron | Gut No. 390/2 | Suresh Swamy | 2.63 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0115 | PRJ-MH-02 | Maharashtra | Latur | Ausa | Ahmedpur | 342/3 | Dnyandev Naik | 3.35 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0466 | PRJ-KA-05 | Karnataka | Bidar | Basavakalyan | Udgir | Gut No. 557/1 | Anil Biradar | 1.57 | Agreement Executed | Disputed | Registered | Fully Paid | 2022-06-12
LND-0418 | PRJ-KA-01 | Karnataka | Bidar | Humnabad | Kamalanagar | Gut No. 790/8 | Revanasiddappa Reddy | 1.4 | Not Started | Pending | Not Registered | Unpaid
LND-0187 | PRJ-MH-04 | Maharashtra | Pune | Baramati | Varkute Malharvadi | 247/4 | Dnyandev Deshmukh | 3.17 | Agreement Executed | Cleared | Not Registered | Partially Paid
LND-0421 | PRJ-KA-07 | Karnataka | Kalaburagi | Kalaburagi | Kalaburagi | Gut No. 705/3 | Lingappa Naik | 1.62 | Agreement Executed | Cleared | Registered | Partially Paid
LND-0255 | PRJ-MH-08 | Maharashtra | Latur | Chakur | Yednapur | 512/3 | Narayan More | 1.65 | Not Started | Pending | Not Registered | Unpaid
LND-0443 | PRJ-KA-07 | Karnataka | Raichur | Sindhanur | Mudgal | 329/6 | Anil Honnalli | 0.61 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0485 | PRJ-KA-06 | Karnataka | Koppal | Gangavathi | Gangavathi | 30/8 | Santosh Reddy | 0.98 | Not Started | Pending | Not Registered | Unpaid
LND-0053 | PRJ-MH-04 | Maharashtra | Pune | Haveli | Lonikand | 816/1 | Narayan Chavan | 2.43 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0459 | PRJ-KA-07 | Karnataka | Gadag | Ron | Gajendragad | 534/2 | Channappa Hosamani | 4.22 | Not Started | Pending | Not Registered | Unpaid
LND-0227 | PRJ-MH-06 | Maharashtra | Osmanabad | Tuljapur | Umarga | 834/5 | Balasaheb Sawant | 0.88 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0055 | PRJ-MH-07 | Maharashtra | Nanded | Hadgaon | Mahur | 851/2 | Santosh Dhole | 1.6 | Agreement Executed | Disputed | Registered | Partially Paid
LND-0301 | PRJ-KA-06 | Karnataka | Vijayapura | Vijayapura | Sindgi | 292/1 | Mahantappa Reddy | 1.23 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0221 | PRJ-MH-08 | Maharashtra | Pune | Indapur | Bhandgaon | 119/3 | Narayan Pawar | 2.04 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0074 | PRJ-MH-05 | Maharashtra | Latur | Chakur | Kinhala | 30/4 | Laxman More | 1.9 | Not Started | Pending | Not Registered | Unpaid
LND-0056 | PRJ-MH-08 | Maharashtra | Osmanabad | Osmanabad | Rui | 364/5 | Bhagwan Mane | 4.46 | MOU Signed | Disputed | Not Registered | Advance Paid
LND-0458 | PRJ-KA-03 | Karnataka | Raichur | Manvi | Hatti | Gut No. 888/8 | Revanasiddappa Kamble | 2.32 | Not Started | Pending | Not Registered | Unpaid
LND-0345 | PRJ-KA-04 | Karnataka | Gadag | Ron | Parasgad | 795/4 | Fakeerappa Hosamani | 1.3 | Not Started | Pending | Not Registered | Unpaid
LND-0202 | PRJ-MH-04 | Maharashtra | Solapur | Barshi | Barshi | 96/7 | Dattatray Bhosale | 2.99 | Not Started | Pending | Not Registered | Unpaid
LND-0103 | PRJ-MH-05 | Maharashtra | Osmanabad | Osmanabad | Naldurg | Gut No. 69/2 | Sopan Jadhav | 0.92 | Not Started | Pending | Not Registered | Unpaid
LND-0252 | PRJ-MH-05 | Maharashtra | Latur | Chakur | Halge | 251/2 | Mahadev Deshmukh | 2.54 | Not Started | Pending | Not Registered | Unpaid
LND-0036 | PRJ-MH-07 | Maharashtra | Nanded | Biloli | Kandhar | 726/7 | Ramesh Naik | 4.67 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0424 | PRJ-KA-06 | Karnataka | Gadag | Ron | Kanaginahal | 71/9 | Hanumantha Hosamani | 1.83 | MOU Signed | Disputed | Not Registered | Partially Paid
LND-0092 | PRJ-MH-08 | Maharashtra | Pune | Haveli | Manjari | Gut No. 938/4 | Ashok Jadhav | 3.36 | Agreement Executed | Disputed | Registered | Partially Paid
LND-0369 | PRJ-KA-01 | Karnataka | Gadag | Ron | Ron | Gut No. 855/5 | Rajesh Bennur | 3.07 | Agreement Executed | Disputed | Registered | Partially Paid
LND-0133 | PRJ-MH-01 | Maharashtra | Solapur | Barshi | Bhalwani | Gut No. 65/2 | Sopan Sutar | 3.19 | Not Started | Pending | Not Registered | Unpaid
LND-0031 | PRJ-MH-06 | Maharashtra | Nanded | Hadgaon | Umri | 948/4 | Raju More | 4.89 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0171 | PRJ-MH-07 | Maharashtra | Osmanabad | Lohara | Washi | 698/3 | Ramesh Chavan | 4.9 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0199 | PRJ-MH-01 | Maharashtra | Pune | Indapur | Nimgaon Ketki | 70/3 | Ramesh Kale | 2.78 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0347 | PRJ-KA-01 | Karnataka | Vijayapura | Sindgi | Nidagundi | 158/6 | Anil Reddy | 3.98 | MOU Signed | Cleared | Not Registered | Partially Paid
LND-0434 | PRJ-KA-08 | Karnataka | Raichur | Raichur | Raichur | Gut No. 611/1 | Ashok Kulkarni | 4.97 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0286 | PRJ-KA-06 | Karnataka | Kalaburagi | Kalaburagi | Jevargi | Gut No. 677/5 | Fakeerappa Hegde | 0.93 | Agreement Executed | Disputed | Not Registered | Partially Paid
LND-0038 | PRJ-MH-03 | Maharashtra | Solapur | Barshi | Kanheri Sarap | 631/5 | Dattatray Chavan | 4.25 | MOU Signed | Cleared | Not Registered | Advance Paid
LND-0083 | PRJ-MH-01 | Maharashtra | Osmanabad | Osmanabad | Yedshi | Gut No. 384/7 | Shankar Gaikwad | 2.89 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0408 | PRJ-KA-01 | Karnataka | Bidar | Humnabad | Nilanga | Gut No. 885/8 | Channappa Bennur | 4.71 | Agreement Executed | Cleared | Not Registered | Fully Paid
LND-0166 | PRJ-MH-06 | Maharashtra | Latur | Chakur | Kinhala | Gut No. 980/3 | Arjun Chavan | 2.04 | MOU Signed | Disputed | Not Registered | Partially Paid
LND-0219 | PRJ-MH-02 | Maharashtra | Solapur | Akkalkot | Mulegaon | 663/1 | Pramod Wagh | 3.55 | Agreement Executed | Disputed | Registered | Partially Paid
LND-0142 | PRJ-MH-07 | Maharashtra | Osmanabad | Lohara | Anatpal | 147/8 | Suresh Kulkarni | 0.8 | MOU Signed | Cleared | Not Registered | Partially Paid
LND-0455 | PRJ-KA-03 | Karnataka | Kalaburagi | Kalaburagi | Sedam | 27/5 | Anil Doddamani | 3.26 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0039 | PRJ-MH-07 | Maharashtra | Nanded | Hadgaon | Bhokar | Gut No. 453/4 | Anil Sutar | 4.07 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0240 | PRJ-MH-01 | Maharashtra | Pune | Baramati | Bhigwan | 128/3 | Arjun Dhole | 0.5 | Agreement Executed | Cleared | Not Registered | Fully Paid
LND-0446 | PRJ-KA-05 | Karnataka | Raichur | Sindhanur | Sindhanur | Gut No. 215/9 | Nagappa Nayak | 2.96 | MOU Signed | Disputed | Not Registered | Partially Paid
LND-0413 | PRJ-KA-07 | Karnataka | Gadag | Gadag | Shirhatti | Gut No. 292/9 | Eranna Kamble | 1.35 | Not Started | Pending | Not Registered | Unpaid
LND-0429 | PRJ-KA-04 | Karnataka | Gadag | Ron | Ron | Gut No. 821/1 | Lingappa Bennur | 3.85 | Agreement Executed | Disputed | Not Registered | Fully Paid
LND-0057 | PRJ-MH-04 | Maharashtra | Pune | Baramati | Varkute Malharvadi | Gut No. 569/4 | Laxman Sutar | 3.41 | Agreement Executed | Disputed | Not Registered | Partially Paid
LND-0095 | PRJ-MH-02 | Maharashtra | Osmanabad | Lohara | Omerga | 408/5 | Ganpat Deshmukh | 4.77 | Agreement Executed | Cleared | Not Registered | Partially Paid
LND-0290 | PRJ-KA-03 | Karnataka | Gadag | Gadag | Gadag | Gut No. 828/9 | Yankappa Doddamani | 1.52 | Not Started | Pending | Not Registered | Unpaid
LND-0193 | PRJ-MH-07 | Maharashtra | Nanded | Biloli | Biloli | 824/9 | Ganpat Sutar | 1.44 | MOU Signed | Cleared | Not Registered | Advance Paid
LND-0067 | PRJ-MH-04 | Maharashtra | Solapur | Barshi | Shegaon | 62/3 | Tukaram Pawar | 3.18 | MOU Signed | Cleared | Not Registered | Advance Paid
LND-0045 | PRJ-MH-07 | Maharashtra | Latur | Ausa | Chakur | Gut No. 426/1 | Ganpat Thorat | 2.25 | Not Started | Pending | Not Registered | Unpaid
LND-0062 | PRJ-MH-01 | Maharashtra | Osmanabad | Tuljapur | Tuljapur | 411/8 | Dnyandev Sawant | 3.33 | Not Started | Pending | Not Registered | Unpaid
LND-0063 | PRJ-MH-03 | Maharashtra | Solapur | Akkalkot | Mulegaon | 255/2 | Vilas Thorat | 3.23 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0112 | PRJ-MH-07 | Maharashtra | Nanded | Biloli | Mukhed | Gut No. 74/7 | Raju Londhe | 0.69 | Not Started | Pending | Not Registered | Unpaid
LND-0030 | PRJ-MH-07 | Maharashtra | Solapur | Mohol | Akluj | Gut No. 921/1 | Narayan Kale | 3.57 | Not Started | Pending | Not Registered | Unpaid
LND-0048 | PRJ-MH-01 | Maharashtra | Pune | Haveli | Wagholi | 888/8 | Pandhari Shinde | 1.67 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0013 | PRJ-MH-02 | Maharashtra | Osmanabad | Tuljapur | Mhaswad | 247/2 | Dnyandev Londhe | 2.69 | Not Started | Pending | Not Registered | Unpaid
LND-0018 | PRJ-MH-02 | Maharashtra | Pune | Indapur | Akluj | Gut No. 820/2 | Rajendra Kale | 1.36 | Agreement Executed | Cleared | Registered | Partially Paid
LND-0099 | PRJ-MH-02 | Maharashtra | Latur | Ausa | Ahmedpur | 463/9 | Rajendra Yadav | 0.7 | MOU Signed | Cleared | Not Registered | Advance Paid
LND-0129 | PRJ-MH-05 | Maharashtra | Latur | Chakur | Halge | Gut No. 94/4 | Sopan Dhole | 4.48 | Not Started | Pending | Not Registered | Unpaid
LND-0146 | PRJ-MH-03 | Maharashtra | Latur | Latur | Renapur | Gut No. 684/6 | Laxman Jadhav | 2.97 | MOU Signed | Cleared | Not Registered | Advance Paid
LND-0113 | PRJ-MH-08 | Maharashtra | Pune | Indapur | Lonand | Gut No. 588/7 | Laxman Wagh | 2.38 | Not Started | Pending | Not Registered | Unpaid
LND-0180 | PRJ-MH-04 | Maharashtra | Solapur | Akkalkot | Wadwal Nagnath | 539/8 | Anil Murkute | 2.13 | Not Started | Pending | Not Registered | Unpaid
LND-0398 | PRJ-KA-08 | Karnataka | Raichur | Raichur | Devadurga | Gut No. 374/7 | Eranna Hosamani | 1.31 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0054 | PRJ-MH-01 | Maharashtra | Latur | Ausa | Ausa | Gut No. 984/6 | Ashok Dhole | 3.68 | Agreement Executed | Cleared | Registered | Fully Paid | 2024-08-10
LND-0269 | PRJ-MH-05 | Maharashtra | Pune | Baramati | Pargaon | 925/8 | Tukaram Kulkarni | 0.91 | MOU Signed | In Progress | Not Registered | Advance Paid
LND-0332 | PRJ-KA-02 | Karnataka | Raichur | Manvi | Manvi | 414/7 | Shivanand Bennur | 2.97 | Not Started | Pending | Not Registered | Unpaid
LND-0211 | PRJ-MH-05 | Maharashtra | Latur | Ausa | Ausa | 586/9 | Pandhari Kadam | 2.21 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0357 | PRJ-KA-08 | Karnataka | Kalaburagi | Sedam | Malkhed | 765/7 | Suresh Rao | 4.82 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0035 | PRJ-MH-01 | Maharashtra | Pune | Haveli | Wagholi | Gut No. 747/6 | Mahadev Yadav | 4.93 | Not Started | Pending | Not Registered | Unpaid
LND-0005 | PRJ-MH-02 | Maharashtra | Pune | Haveli | Koregaon Bhima | Gut No. 82/4 | Raju Deshmukh | 2.21 | Agreement Executed | Disputed | Not Registered | Fully Paid
LND-0457 | PRJ-KA-03 | Karnataka | Kalaburagi | Kalaburagi | Kalaburagi | Gut No. 783/1 | Eranna Kamble | 1.5 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0281 | PRJ-KA-04 | Karnataka | Gadag | Gadag | Ron | 340/2 | Revanasiddappa Angadi | 4.92 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0161 | PRJ-MH-03 | Maharashtra | Solapur | Akkalkot | Wadwal Nagnath | Gut No. 513/1 | Suresh Shinde | 1.12 | MOU Signed | Cleared | Not Registered | Partially Paid
LND-0391 | PRJ-KA-08 | Karnataka | Bidar | Basavakalyan | Basavakalyan | Gut No. 649/4 | Santosh Hegde | 4.1 | Agreement Executed | Disputed | Not Registered | Fully Paid
LND-0173 | PRJ-MH-07 | Maharashtra | Solapur | Mohol | Karkamb | Gut No. 807/8 | Pandhari Londhe | 4.83 | MOU Signed | In Progress | Not Registered | Advance Paid
LND-0267 | PRJ-MH-05 | Maharashtra | Osmanabad | Osmanabad | Osmanabad | Gut No. 876/8 | Vilas Londhe | 2.98 | Not Started | Pending | Not Registered | Unpaid
LND-0100 | PRJ-MH-01 | Maharashtra | Latur | Ausa | Deoni | 503/8 | Dnyandev Jadhav | 1.95 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0302 | PRJ-KA-04 | Karnataka | Vijayapura | Muddebihal | Almel | 886/1 | Devendrappa Kulkarni | 3.41 | Not Started | Pending | Not Registered | Unpaid
LND-0124 | PRJ-MH-05 | Maharashtra | Solapur | Mohol | Akluj | Gut No. 197/4 | Shankar Kulkarni | 0.85 | Not Started | Pending | Not Registered | Unpaid
LND-0237 | PRJ-MH-07 | Maharashtra | Latur | Latur | Renapur | 413/9 | Shriram Mane | 3.63 | MOU Signed | Cleared | Not Registered | Partially Paid
LND-0201 | PRJ-MH-03 | Maharashtra | Pune | Baramati | Morgaon | 197/9 | Santosh Waghmare | 1.7 | Agreement Executed | Cleared | Registered | Fully Paid | 2024-07-29
LND-0300 | PRJ-KA-05 | Karnataka | Vijayapura | Sindgi | Kolhar | Gut No. 651/2 | Santosh Patil | 1.59 | Agreement Executed | Disputed | Not Registered | Fully Paid
LND-0131 | PRJ-MH-03 | Maharashtra | Solapur | Mohol | Akluj | Gut No. 713/3 | Kisan Murkute | 2.61 | Not Started | Pending | Not Registered | Unpaid
LND-0051 | PRJ-MH-08 | Maharashtra | Pune | Haveli | Koregaon Bhima | Gut No. 717/5 | Kisan Waghmare | 1.26 | Not Started | Pending | Not Registered | Unpaid
LND-0137 | PRJ-MH-08 | Maharashtra | Latur | Chakur | Halge | 65/8 | Suresh Pawar | 1.41 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0139 | PRJ-MH-05 | Maharashtra | Pune | Indapur | Bhandgaon | Gut No. 762/8 | Dattatray Salve | 4.88 | Agreement Executed | Disputed | Registered | Fully Paid | 2022-06-19
LND-0172 | PRJ-MH-08 | Maharashtra | Solapur | Barshi | Natepute | Gut No. 662/1 | Kisan Jadhav | 3.44 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0140 | PRJ-MH-07 | Maharashtra | Pune | Indapur | Lonand | 559/5 | Bhagwan Deshmukh | 0.86 | MOU Signed | Cleared | Not Registered | Partially Paid
LND-0334 | PRJ-KA-02 | Karnataka | Bidar | Humnabad | Kamalanagar | 350/6 | Prakash Rao | 2.96 | MOU Signed | Disputed | Not Registered | Advance Paid
LND-0477 | PRJ-KA-03 | Karnataka | Vijayapura | Vijayapura | Sindgi | Gut No. 642/9 | Siddappa Doddamani | 3.23 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0222 | PRJ-MH-08 | Maharashtra | Pune | Indapur | Akluj | Gut No. 327/2 | Popat Shinde | 4.15 | Not Started | Pending | Not Registered | Unpaid
LND-0182 | PRJ-MH-08 | Maharashtra | Pune | Indapur | Nimgaon Ketki | Gut No. 468/1 | Vilas Dhole | 3.53 | MOU Signed | Disputed | Not Registered | Advance Paid
LND-0451 | PRJ-KA-04 | Karnataka | Koppal | Gangavathi | Gangavathi | Gut No. 900/7 | Basavaraj Bennur | 4.77 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0360 | PRJ-KA-03 | Karnataka | Gadag | Gadag | Shirhatti | Gut No. 661/9 | Mallappa Rao | 3.52 | MOU Signed | In Progress | Not Registered | Advance Paid
LND-0050 | PRJ-MH-06 | Maharashtra | Solapur | Akkalkot | Akkalkot | 773/1 | Rajendra Kale | 4.28 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0022 | PRJ-MH-01 | Maharashtra | Nanded | Biloli | Naigaon | Gut No. 59/1 | Pramod Sutar | 2.76 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0352 | PRJ-KA-04 | Karnataka | Vijayapura | Muddebihal | Muddebihal | 172/9 | Suresh Patil | 3.32 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0162 | PRJ-MH-03 | Maharashtra | Nanded | Biloli | Kandhar | Gut No. 167/7 | Balasaheb Londhe | 4.29 | MOU Signed | Disputed | Not Registered | Partially Paid
LND-0196 | PRJ-MH-06 | Maharashtra | Latur | Latur | Jalkot | 760/3 | Ramesh Mane | 2.99 | Agreement Executed | Disputed | Not Registered | Partially Paid
LND-0230 | PRJ-MH-06 | Maharashtra | Pune | Indapur | Nimgaon Ketki | 835/7 | Vilas Naik | 3.44 | Agreement Executed | Disputed | Registered | Fully Paid | 2024-09-27
LND-0148 | PRJ-MH-02 | Maharashtra | Pune | Indapur | Bhandgaon | Gut No. 539/7 | Kisan Thorat | 4.21 | Not Started | Pending | Not Registered | Unpaid
LND-0007 | PRJ-MH-06 | Maharashtra | Pune | Baramati | Malegaon | Gut No. 411/5 | Dnyandev Kale | 4.61 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0223 | PRJ-MH-01 | Maharashtra | Osmanabad | Lohara | Lohara | 953/4 | Anil More | 2.98 | MOU Signed | Disputed | Not Registered | Partially Paid
LND-0272 | PRJ-KA-07 | Karnataka | Kalaburagi | Yadgir | Shorapur | 646/9 | Basavaraj Lamani | 4.02 | MOU Signed | Cleared | Not Registered | Partially Paid
LND-0386 | PRJ-KA-04 | Karnataka | Bidar | Humnabad | Gadlegaon | 630/3 | Santosh Reddy | 2.12 | Not Started | Pending | Not Registered | Unpaid
LND-0135 | PRJ-MH-06 | Maharashtra | Pune | Haveli | Manjari | 400/8 | Suresh Wagh | 2.24 | MOU Signed | Cleared | Not Registered | Advance Paid
LND-0432 | PRJ-KA-07 | Karnataka | Bidar | Bidar | Humnabad | Gut No. 517/6 | Santosh Desai | 2.9 | Agreement Executed | Disputed | Registered | Fully Paid | 2024-02-01
LND-0200 | PRJ-MH-08 | Maharashtra | Pune | Baramati | Varkute Malharvadi | 18/9 | Shriram Mane | 2.91 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0350 | PRJ-KA-08 | Karnataka | Kalaburagi | Sedam | Kamalapur | 982/1 | Santosh Hugar | 2.22 | Not Started | Pending | Not Registered | Unpaid
LND-0195 | PRJ-MH-08 | Maharashtra | Nanded | Hadgaon | Mahur | Gut No. 369/9 | Sanjay Dhole | 0.94 | Agreement Executed | Disputed | Not Registered | Fully Paid
LND-0120 | PRJ-MH-02 | Maharashtra | Osmanabad | Lohara | Lohara | 41/4 | Laxman Dhole | 4.96 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0273 | PRJ-KA-06 | Karnataka | Koppal | Kushtagi | Bettadur | Gut No. 277/3 | Basavaraj Hugar | 3.19 | Not Started | Pending | Not Registered | Unpaid
LND-0363 | PRJ-KA-07 | Karnataka | Vijayapura | Sindgi | Nidagundi | Gut No. 899/8 | Channappa Hosamani | 2.11 | MOU Signed | Cleared | Not Registered | Advance Paid
LND-0155 | PRJ-MH-07 | Maharashtra | Solapur | Barshi | Bhalwani | 327/4 | Arjun Deshmukh | 1.7 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0244 | PRJ-MH-02 | Maharashtra | Osmanabad | Tuljapur | Murud | 392/3 | Ashok Kadam | 1.14 | Not Started | Pending | Not Registered | Unpaid
LND-0205 | PRJ-MH-03 | Maharashtra | Osmanabad | Osmanabad | Kalamb | 771/7 | Dnyandev Pawar | 1.23 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0238 | PRJ-MH-06 | Maharashtra | Nanded | Biloli | Naigaon | 749/8 | Ashok Kadam | 3.64 | Not Started | Pending | Not Registered | Unpaid
LND-0488 | PRJ-KA-03 | Karnataka | Koppal | Gangavathi | Hospet | Gut No. 188/6 | Gurusiddappa Hosamani | 2.69 | Not Started | Pending | Not Registered | Unpaid
LND-0428 | PRJ-KA-07 | Karnataka | Gadag | Ron | Parasgad | Gut No. 51/6 | Revanasiddappa Gudadinni | 3.73 | Not Started | Pending | Not Registered | Unpaid
LND-0060 | PRJ-MH-08 | Maharashtra | Osmanabad | Lohara | Bhoom | Gut No. 103/4 | Popat Gaikwad | 2.12 | MOU Signed | In Progress | Not Registered | Advance Paid
LND-0136 | PRJ-MH-06 | Maharashtra | Pune | Indapur | Nimgaon Ketki | 791/6 | Shankar Shinde | 2.09 | MOU Signed | Disputed | Not Registered | Advance Paid
LND-0329 | PRJ-KA-07 | Karnataka | Gadag | Gadag | Ron | Gut No. 680/7 | Hanumantha Bennur | 4.51 | Not Started | Pending | Not Registered | Unpaid
LND-0461 | PRJ-KA-07 | Karnataka | Vijayapura | Sindgi | Talikot | 433/5 | Anil Reddy | 3.6 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0177 | PRJ-MH-04 | Maharashtra | Pune | Indapur | Bhandgaon | 458/5 | Bhagwan Pawar | 3.12 | Not Started | Pending | Not Registered | Unpaid
LND-0296 | PRJ-KA-07 | Karnataka | Kalaburagi | Sedam | Kamalapur | Gut No. 40/7 | Gurusiddappa Hegde | 0.72 | Agreement Executed | Disputed | Registered | Partially Paid
LND-0108 | PRJ-MH-06 | Maharashtra | Osmanabad | Lohara | Omerga | 905/1 | Shankar More | 3.89 | Not Started | Pending | Not Registered | Unpaid
LND-0444 | PRJ-KA-08 | Karnataka | Koppal | Koppal | Yelburga | 947/4 | Nagappa Angadi | 1.2 | Not Started | Pending | Not Registered | Unpaid
LND-0327 | PRJ-KA-06 | Karnataka | Koppal | Koppal | Gangavathi | Gut No. 943/8 | Veeranna Kamble | 2.48 | Not Started | Pending | Not Registered | Unpaid
LND-0372 | PRJ-KA-04 | Karnataka | Raichur | Sindhanur | Sindhanur | Gut No. 692/8 | Devendrappa Nayak | 3.16 | Agreement Executed | Cleared | Not Registered | Partially Paid
LND-0226 | PRJ-MH-04 | Maharashtra | Latur | Latur | Murud | Gut No. 541/6 | Balasaheb Bhosale | 3.25 | Not Started | Pending | Not Registered | Unpaid
LND-0339 | PRJ-KA-03 | Karnataka | Raichur | Manvi | Kavital | Gut No. 864/9 | Gurusiddappa Bennur | 3.35 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0122 | PRJ-MH-06 | Maharashtra | Pune | Haveli | Koregaon Bhima | Gut No. 318/7 | Shankar Yadav | 3.69 | Not Started | Pending | Not Registered | Unpaid
LND-0197 | PRJ-MH-06 | Maharashtra | Solapur | Barshi | Bhalwani | 512/9 | Ashok Kadam | 2.02 | Agreement Executed | Disputed | Registered | Partially Paid
LND-0212 | PRJ-MH-05 | Maharashtra | Latur | Latur | Latur | 446/5 | Mahadev Pawar | 2.68 | Not Started | Pending | Not Registered | Unpaid
LND-0254 | PRJ-MH-03 | Maharashtra | Osmanabad | Lohara | Lohara | 344/7 | Santosh Naik | 0.79 | Not Started | Pending | Not Registered | Unpaid
LND-0079 | PRJ-MH-06 | Maharashtra | Latur | Chakur | Kinhala | Gut No. 680/3 | Sanjay Shinde | 1.07 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0305 | PRJ-KA-05 | Karnataka | Vijayapura | Muddebihal | Devara Hippargi | 154/9 | Nagaraj Hegde | 4.55 | Agreement Executed | Disputed | Not Registered | Partially Paid
LND-0075 | PRJ-MH-07 | Maharashtra | Pune | Baramati | Pargaon | Gut No. 970/2 | Ashok Kulkarni | 2.74 | MOU Signed | Disputed | Not Registered | Partially Paid
LND-0044 | PRJ-MH-05 | Maharashtra | Solapur | Barshi | Natepute | Gut No. 915/9 | Dnyandev Kulkarni | 1.18 | Agreement Executed | Cleared | Not Registered | Partially Paid
LND-0460 | PRJ-KA-04 | Karnataka | Koppal | Kushtagi | Kinnal | 572/7 | Ashok Honnalli | 4.83 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0017 | PRJ-MH-04 | Maharashtra | Latur | Ausa | Nilanga | 100/7 | Narayan Thorat | 2.35 | Not Started | Pending | Not Registered | Unpaid
LND-0271 | PRJ-KA-05 | Karnataka | Vijayapura | Sindgi | Nidagundi | 629/4 | Prakash Rao | 2.75 | Agreement Executed | Cleared | Not Registered | Fully Paid
LND-0093 | PRJ-MH-03 | Maharashtra | Pune | Baramati | Undewadi | Gut No. 119/2 | Rajendra Chavan | 1.11 | Agreement Executed | Disputed | Registered | Partially Paid
LND-0420 | PRJ-KA-04 | Karnataka | Vijayapura | Vijayapura | Basavana Bagewadi | 242/7 | Gurusiddappa Patil | 1.25 | MOU Signed | Disputed | Not Registered | Advance Paid
LND-0121 | PRJ-MH-05 | Maharashtra | Latur | Ausa | Ahmedpur | 809/6 | Dnyandev Salve | 0.93 | Agreement Executed | Disputed | Registered | Partially Paid
LND-0359 | PRJ-KA-05 | Karnataka | Kalaburagi | Sedam | Devara Hippargi | 423/9 | Hanumantha Desai | 1.33 | MOU Signed | In Progress | Not Registered | Advance Paid
LND-0435 | PRJ-KA-04 | Karnataka | Kalaburagi | Yadgir | Yadgir | Gut No. 942/9 | Ashok Bennur | 3.07 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0403 | PRJ-KA-06 | Karnataka | Vijayapura | Muddebihal | Horti | Gut No. 794/8 | Mallappa Lamani | 3.26 | Agreement Executed | Cleared | Not Registered | Fully Paid
LND-0190 | PRJ-MH-01 | Maharashtra | Osmanabad | Lohara | Washi | Gut No. 714/7 | Mahadev Kulkarni | 1.85 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0229 | PRJ-MH-03 | Maharashtra | Latur | Chakur | Salegaon | 569/3 | Sanjay Pawar | 1.13 | MOU Signed | Cleared | Not Registered | Advance Paid
LND-0338 | PRJ-KA-07 | Karnataka | Gadag | Ron | Parasgad | Gut No. 429/4 | Eranna Lamani | 4.84 | MOU Signed | Cleared | Not Registered | Advance Paid
LND-0078 | PRJ-MH-06 | Maharashtra | Nanded | Hadgaon | Bhokar | Gut No. 891/4 | Laxman Gaikwad | 3.07 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0379 | PRJ-KA-07 | Karnataka | Kalaburagi | Yadgir | Hunasagi | 932/2 | Fakeerappa Gudadinni | 4.45 | Agreement Executed | Disputed | Not Registered | Partially Paid
LND-0303 | PRJ-KA-04 | Karnataka | Vijayapura | Muddebihal | Devara Hippargi | Gut No. 434/7 | Lingappa Hosamani | 1.63 | Agreement Executed | Disputed | Registered | Partially Paid
LND-0090 | PRJ-MH-08 | Maharashtra | Osmanabad | Lohara | Omerga | 480/2 | Shankar Gaikwad | 4.37 | Agreement Executed | Disputed | Not Registered | Fully Paid
LND-0310 | PRJ-KA-08 | Karnataka | Kalaburagi | Sedam | Sedam | Gut No. 543/5 | Yankappa Reddy | 4.42 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0496 | PRJ-KA-01 | Karnataka | Gadag | Ron | Ron | Gut No. 887/1 | Revanasiddappa Kamble | 3.66 | Agreement Executed | Disputed | Registered | Fully Paid | 2024-02-21
LND-0472 | PRJ-KA-08 | Karnataka | Raichur | Raichur | Lingsugur | 726/5 | Nagappa Patil | 1.03 | Agreement Executed | Cleared | Not Registered | Fully Paid
LND-0008 | PRJ-MH-07 | Maharashtra | Latur | Latur | Murud | 253/9 | Vilas Mane | 3.86 | Agreement Executed | Disputed | Registered | Partially Paid
LND-0132 | PRJ-MH-02 | Maharashtra | Pune | Indapur | Nimgaon Ketki | 562/9 | Mahadev Deshmukh | 3.99 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0141 | PRJ-MH-07 | Maharashtra | Solapur | Akkalkot | Khanderajuri | Gut No. 458/1 | Shriram Waghmare | 3.27 | Agreement Executed | Disputed | Not Registered | Partially Paid
LND-0483 | PRJ-KA-06 | Karnataka | Raichur | Manvi | Manvi | Gut No. 153/3 | Eranna Gowda | 0.57 | Not Started | Pending | Not Registered | Unpaid
LND-0316 | PRJ-KA-01 | Karnataka | Kalaburagi | Kalaburagi | Yadgir | 217/1 | Rajesh Hiremath | 1.26 | MOU Signed | Disputed | Not Registered | Advance Paid
LND-0068 | PRJ-MH-08 | Maharashtra | Osmanabad | Lohara | Washi | Gut No. 513/9 | Sanjay Dhole | 0.86 | Not Started | Pending | Not Registered | Unpaid
LND-0130 | PRJ-MH-07 | Maharashtra | Pune | Indapur | Lonand | Gut No. 242/7 | Dnyandev Waghmare | 1.51 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0143 | PRJ-MH-01 | Maharashtra | Nanded | Biloli | Naigaon | Gut No. 972/6 | Narayan Dhole | 3.93 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0437 | PRJ-KA-07 | Karnataka | Koppal | Koppal | Koppal | Gut No. 812/8 | Siddappa Biradar | 4.22 | Not Started | Pending | Not Registered | Unpaid
LND-0469 | PRJ-KA-03 | Karnataka | Raichur | Manvi | Kavital | Gut No. 954/1 | Mallappa Rao | 1.95 | Agreement Executed | Cleared | Registered | Partially Paid
LND-0259 | PRJ-MH-08 | Maharashtra | Pune | Indapur | Nimgaon Ketki | Gut No. 578/5 | Shriram Yadav | 1.59 | MOU Signed | Disputed | Not Registered | Partially Paid
LND-0065 | PRJ-MH-02 | Maharashtra | Solapur | Mohol | Sangola | 161/1 | Mahadev Dhole | 3.6 | Agreement Executed | Disputed | Not Registered | Partially Paid
LND-0043 | PRJ-MH-08 | Maharashtra | Solapur | Akkalkot | Khanderajuri | Gut No. 266/4 | Sopan Wagh | 1.75 | Agreement Executed | Cleared | Registered | Fully Paid | 2022-06-08
LND-0249 | PRJ-MH-07 | Maharashtra | Osmanabad | Lohara | Anatpal | Gut No. 978/2 | Ramesh Sawant | 0.8 | MOU Signed | In Progress | Not Registered | Advance Paid
LND-0147 | PRJ-MH-03 | Maharashtra | Osmanabad | Lohara | Anatpal | 206/3 | Rajendra Sutar | 0.62 | MOU Signed | Cleared | Not Registered | Advance Paid
LND-0014 | PRJ-MH-03 | Maharashtra | Solapur | Akkalkot | Khanderajuri | 272/9 | Raju Yadav | 2.4 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0320 | PRJ-KA-05 | Karnataka | Bidar | Bidar | Aurad | 624/4 | Nagaraj Swamy | 4.24 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0378 | PRJ-KA-07 | Karnataka | Koppal | Gangavathi | Hospet | 715/9 | Yankappa Hegde | 4.72 | Agreement Executed | Disputed | Registered | Partially Paid
LND-0415 | PRJ-KA-01 | Karnataka | Koppal | Koppal | Gangavathi | 289/5 | Hanumantha Hosamani | 3.77 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0150 | PRJ-MH-01 | Maharashtra | Pune | Haveli | Koregaon Bhima | Gut No. 169/3 | Bhagwan Murkute | 1.51 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0337 | PRJ-KA-01 | Karnataka | Koppal | Gangavathi | Hampi | Gut No. 947/9 | Nagaraj Desai | 3.61 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0027 | PRJ-MH-02 | Maharashtra | Solapur | Barshi | Barshi | 761/9 | Shankar Mane | 1.77 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0452 | PRJ-KA-07 | Karnataka | Gadag | Gadag | Gadag | Gut No. 534/4 | Yankappa Hegde | 3.08 | Agreement Executed | Disputed | Registered | Fully Paid | 2022-09-27
LND-0087 | PRJ-MH-05 | Maharashtra | Pune | Haveli | Uruli Kanchan | Gut No. 853/5 | Kisan Gaikwad | 3.23 | MOU Signed | In Progress | Not Registered | Advance Paid
LND-0464 | PRJ-KA-07 | Karnataka | Gadag | Gadag | Ron | Gut No. 45/3 | Gurusiddappa Doddamani | 4.42 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0243 | PRJ-MH-01 | Maharashtra | Osmanabad | Osmanabad | Rui | 490/2 | Rajendra Bhosale | 0.9 | Not Started | Pending | Not Registered | Unpaid
LND-0473 | PRJ-KA-07 | Karnataka | Bidar | Basavakalyan | Hulsoor | 2026-12-04 | Ramesh Rao | 1.64 | Not Started | Pending | Not Registered | Unpaid
LND-0032 | PRJ-MH-03 | Maharashtra | Osmanabad | Tuljapur | Mhaswad | Gut No. 164/2 | Dattatray Shinde | 4.36 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0134 | PRJ-MH-04 | Maharashtra | Solapur | Barshi | Kanheri Sarap | 630/6 | Rajendra Sawant | 2.37 | Not Started | Pending | Not Registered | Unpaid
LND-0289 | PRJ-KA-06 | Karnataka | Kalaburagi | Yadgir | Yadgir | Gut No. 451/8 | Eranna Hegde | 4.27 | Not Started | Pending | Not Registered | Unpaid
LND-0402 | PRJ-KA-06 | Karnataka | Koppal | Kushtagi | Bettadur | Gut No. 21/7 | Veeranna Angadi | 4.4 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0373 | PRJ-KA-03 | Karnataka | Koppal | Kushtagi | Guttal | 645/9 | Shivanand Doddamani | 1.16 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0156 | PRJ-MH-01 | Maharashtra | Osmanabad | Tuljapur | Umarga | Gut No. 255/3 | Sopan Salve | 4.7 | MOU Signed | In Progress | Not Registered | Advance Paid
LND-0384 | PRJ-KA-07 | Karnataka | Gadag | Gadag | Gadag | 483/7 | Mallappa Naik | 1.68 | MOU Signed | In Progress | Not Registered | Advance Paid
LND-0306 | PRJ-KA-08 | Karnataka | Vijayapura | Sindgi | Talikot | Gut No. 398/1 | Rajesh Doddamani | 4.17 | MOU Signed | Disputed | Not Registered | Advance Paid
LND-0356 | PRJ-KA-06 | Karnataka | Koppal | Koppal | Kushtagi | Gut No. 622/2 | Fakeerappa Hosamani | 2.22 | Not Started | Pending | Not Registered | Unpaid
LND-0019 | PRJ-MH-05 | Maharashtra | Latur | Latur | Latur | Gut No. 828/9 | Vitthal Shinde | 3.43 | Not Started | Pending | Not Registered | Unpaid
LND-0086 | PRJ-MH-07 | Maharashtra | Latur | Latur | Udgir | Gut No. 586/6 | Pramod Pawar | 4.97 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0149 | PRJ-MH-03 | Maharashtra | Osmanabad | Lohara | Lohara | Gut No. 478/9 | Narayan Kulkarni | 4.45 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0151 | PRJ-MH-04 | Maharashtra | Nanded | Hadgaon | Kinwat | Gut No. 630/9 | Dnyandev Naik | 3.38 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0465 | PRJ-KA-03 | Karnataka | Gadag | Gadag | Ron | Gut No. 317/8 | Fakeerappa Honnalli | 1.31 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0181 | PRJ-MH-01 | Maharashtra | Nanded | Biloli | Mukhed | 169/6 | Raju Naik | 2.49 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0216 | PRJ-MH-07 | Maharashtra | Osmanabad | Osmanabad | Shirur Anantpal | 607/9 | Pandhari Kadam | 3.95 | Not Started | Pending | Not Registered | Unpaid
LND-0170 | PRJ-MH-03 | Maharashtra | Pune | Haveli | Manjari | 249/1 | Subhash Naik | 1.52 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0376 | PRJ-KA-04 | Karnataka | Raichur | Sindhanur | Maski | 17/4 | Ashok Hiremath | 3.58 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0294 | PRJ-KA-01 | Karnataka | Gadag | Ron | Ron | Gut No. 154/3 | Rajesh Doddamani | 3.12 | Not Started | Pending | Not Registered | Unpaid
LND-0478 | PRJ-KA-06 | Karnataka | Gadag | Gadag | Nargund | Gut No. 89/8 | Revanasiddappa Angadi | 2.53 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0263 | PRJ-MH-07 | Maharashtra | Pune | Haveli | Manjari | 446/3 | Rajendra Pawar | 1.67 | MOU Signed | Cleared | Not Registered | Partially Paid
LND-0233 | PRJ-MH-04 | Maharashtra | Osmanabad | Osmanabad | Rui | Gut No. 357/2 | Arjun Deshmukh | 3.99 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0241 | PRJ-MH-03 | Maharashtra | Osmanabad | Osmanabad | Naldurg | Gut No. 257/2 | Narayan Kadam | 4.57 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0006 | PRJ-MH-06 | Maharashtra | Solapur | Akkalkot | Mulegaon | 624/3 | Vilas Londhe | 1.6 | Agreement Executed | Disputed | Registered | Partially Paid
LND-0484 | PRJ-KA-04 | Karnataka | Koppal | Gangavathi | Hampi | Gut No. 278/3 | Ramesh Rao | 3.08 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0274 | PRJ-KA-05 | Karnataka | Bidar | Basavakalyan | Wadi | Gut No. 786/4 | Siddappa Gowda | 1.62 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0176 | PRJ-MH-03 | Maharashtra | Nanded | Hadgaon | Bhokar | Gut No. 89/7 | Subhash Deshmukh | 1.33 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0028 | PRJ-MH-05 | Maharashtra | Nanded | Hadgaon | Mahur | 95/7 | Sopan Mane | 0.7 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0314 | PRJ-KA-04 | Karnataka | Kalaburagi | Sedam | Devara Hippargi | Gut No. 133/2 | Mahantappa Hiremath | 3.15 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0160 | PRJ-MH-07 | Maharashtra | Nanded | Hadgaon | Umri | Gut No. 846/2 | Shankar Deshmukh | 2.27 | MOU Signed | Disputed | Not Registered | Partially Paid
LND-0297 | PRJ-KA-06 | Karnataka | Vijayapura | Sindgi | Tikota | Gut No. 879/2 | Revanasiddappa Kulkarni | 1.85 | Agreement Executed | Disputed | Registered | Fully Paid | 2022-07-02
LND-0409 | PRJ-KA-07 | Karnataka | Koppal | Kushtagi | Hiregonagar | Gut No. 931/6 | Devendrappa Bennur | 1.52 | Not Started | Pending | Not Registered | Unpaid
LND-0277 | PRJ-KA-02 | Karnataka | Bidar | Bidar | Chitaguppa | 21/9 | Devendrappa Patil | 1.99 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0325 | PRJ-KA-06 | Karnataka | Raichur | Manvi | Yaragera | 382/6 | Siddappa Gowda | 2.3 | Agreement Executed | Disputed | Registered | Fully Paid | 2024-05-13
LND-0351 | PRJ-KA-07 | Karnataka | Vijayapura | Muddebihal | Devara Hippargi | 934/9 | Nagaraj Angadi | 2.81 | Agreement Executed | Disputed | Not Registered | Fully Paid
LND-0040 | PRJ-MH-06 | Maharashtra | Pune | Baramati | Undewadi | 826/4 | Shankar Patil | 0.71 | Agreement Executed | Cleared | Registered | Fully Paid | 2023-02-03
LND-0343 | PRJ-KA-05 | Karnataka | Kalaburagi | Sedam | Sedam | Gut No. 834/8 | Veeranna Gudadinni | 4.41 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0340 | PRJ-KA-06 | Karnataka | Gadag | Gadag | Mundargi | 516/9 | Ramesh Honnalli | 1.95 | Not Started | Pending | Not Registered | Unpaid
LND-0380 | PRJ-KA-01 | Karnataka | Koppal | Kushtagi | Kushtagi | 385/4 | Ramesh Hugar | 2.34 | Not Started | Pending | Not Registered | Unpaid
LND-0323 | PRJ-KA-05 | Karnataka | Gadag | Gadag | Ron | Gut No. 271/8 | Shivanand Gowda | 4.16 | Not Started | Pending | Not Registered | Unpaid
LND-0242 | PRJ-MH-05 | Maharashtra | Solapur | Barshi | Barshi | 2026-02-04 | Sanjay Jadhav | 1.1 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0126 | PRJ-MH-07 | Maharashtra | Osmanabad | Lohara | Anatpal | Gut No. 626/5 | Kisan Londhe | 4.03 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0046 | PRJ-MH-07 | Maharashtra | Latur | Latur | Murud | Gut No. 772/7 | Raju Thorat | 2.92 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0313 | PRJ-KA-07 | Karnataka | Bidar | Bidar | Chitaguppa | 749/6 | Basavaraj Hugar | 3.91 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0456 | PRJ-KA-06 | Karnataka | Bidar | Humnabad | Saidapur | 515/8 | Ramesh Honnalli | 2.18 | Agreement Executed | Disputed | Registered | Partially Paid
LND-0268 | PRJ-MH-08 | Maharashtra | Pune | Baramati | Pargaon | 64/4 | Shankar Kale | 4.21 | MOU Signed | Disputed | Not Registered | Advance Paid
LND-0491 | PRJ-KA-07 | Karnataka | Bidar | Basavakalyan | Kamalnagar | Gut No. 804/7 | Rajesh Hugar | 2.95 | Under Negotiation | Pending | Not Registered | Unpaid
LND-0265 | PRJ-MH-03 | Maharashtra | Latur | Ausa | Ahmedpur | Gut No. 124/9 | Narayan Kale | 2.53 | Agreement Executed | Disputed | Not Registered | Partially Paid
LND-0239 | PRJ-MH-07 | Maharashtra | Solapur | Barshi | Shegaon | Gut No. 275/6 | Sopan Pawar | 2.02 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0144 | PRJ-MH-06 | Maharashtra | Osmanabad | Osmanabad | Osmanabad | 754/3 | Sanjay Naik | 2.24 | Not Started | Pending | Not Registered | Unpaid
LND-0399 | PRJ-KA-05 | Karnataka | Kalaburagi | Sedam | Sannati | Gut No. 201/3 | Srinivas Kulkarni | 2.63 | Not Started | Pending | Not Registered | Unpaid
LND-0385 | PRJ-KA-07 | Karnataka | Raichur | Manvi | Kavital | Gut No. 729/1 | Nagaraj Desai | 3.38 | Agreement Executed | Cleared | Not Registered | Fully Paid
LND-0440 | PRJ-KA-03 | Karnataka | Bidar | Humnabad | Saidapur | Gut No. 771/9 | Mallappa Hegde | 2.44 | Agreement Executed | Cleared | Not Registered | Fully Paid
LND-0270 | PRJ-MH-08 | Maharashtra | Pune | Baramati | Varkute Malharvadi | Gut No. 509/1 | Dattatray Kadam | 2.42 | MOU Signed | In Progress | Not Registered | Advance Paid
LND-0375 | PRJ-KA-07 | Karnataka | Koppal | Koppal | Kanakagiri | 639/9 | Eranna Desai | 3.76 | MOU Signed | Cleared | Not Registered | Advance Paid
LND-0374 | PRJ-KA-07 | Karnataka | Koppal | Kushtagi | Kushtagi | Gut No. 970/2 | Nagappa Hosamani | 3.23 | Agreement Executed | Disputed | Not Registered | Partially Paid
LND-0073 | PRJ-MH-08 | Maharashtra | Latur | Latur | Udgir | Gut No. 638/8 | Ashok Dhole | 3.92 | Under Negotiation | In Progress | Not Registered | Unpaid
LND-0041 | PRJ-MH-07 | Maharashtra | Latur | Ausa | Nilanga | 672/1 | Kisan Deshmukh | 4 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0354 | PRJ-KA-02 | Karnataka | Bidar | Bidar | Humnabad | Gut No. 572/2 | Rajesh Hegde | 4.6 | Agreement Executed | Disputed | Registered | Fully Paid | 2024-06-05
LND-0493 | PRJ-KA-06 | Karnataka | Raichur | Manvi | Manvi | 223/3 | Rajesh Honnalli | 4.14 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0247 | PRJ-MH-04 | Maharashtra | Nanded | Hadgaon | Hadgaon | Gut No. 211/9 | Balasaheb Naik | 1.35 | Agreement Executed | Disputed | Not Registered | Partially Paid
LND-0298 | PRJ-KA-04 | Karnataka | Raichur | Raichur | Devadurga | Gut No. 778/9 | Lingappa Reddy | 2.82 | Under Negotiation | Pending | Not Registered | Advance Paid
LND-0058 | PRJ-MH-05 | Maharashtra | Solapur | Barshi | Shegaon | Gut No. 680/6 | Sanjay Chavan | 2.89 | Agreement Executed | Disputed | Registered | Fully Paid | 2023-07-09
LND-0189 | PRJ-MH-04 | Maharashtra | Osmanabad | Osmanabad | Naldurg | 424/5 | Santosh Shinde | 3.01 | Under Negotiation | In Progress | Not Registered | Advance Paid
LND-0361 | PRJ-KA-08 | Karnataka | Vijayapura | Sindgi | Nidagundi | 103/5 | Anil Naik | 4.55 | MOU Signed | Cleared | Not Registered | Partially Paid
LND-0248 | PRJ-MH-08 | Maharashtra | Latur | Latur | Udgir | Gut No. 654/2 | Anil Patil | 4.94 | MOU Signed | In Progress | Not Registered | Partially Paid
LND-0291 | PRJ-KA-07 | Karnataka | Koppal | Gangavathi | Hampi | Gut No. 587/4 | Devendrappa Rao | 0.86 | Not Started | Pending | Not Registered | Unpaid
1408.53

## project_overview
Project_ID | Project_Name | State | District | Energy_Type | Capacity_MW | Land_Required_Acres | Expected_Commission_Date | Project_Status
PRJ-MH-01 | Baramati Solar Energy Park | Maharashtra | Pune | Solar | 50 | 250 | 2025-03-31 | Under Construction
PRJ-MH-02 | Solapur Surya Urja Project | Maharashtra | Solapur | Solar | 100 | 500 | 2025-09-30 | Land Acquisition
PRJ-MH-03 | Osmanabad Renewable Power Initiative | Maharashtra | Osmanabad | Solar | 75 | 375 | 2026-03-31 | Land Acquisition
PRJ-MH-04 | Latur Sun Power Station | Maharashtra | Latur | Solar | 60 | 300 | 2024-12-31 | Completed
PRJ-MH-05 | Nanded Solar Agri Park | Maharashtra | Nanded | Solar | 40 | 200 | 2026-06-30 | Planning
PRJ-MH-06 | Marathwada Wind Energy Project | Maharashtra | Osmanabad | Wind | 80 | 480 | 2025-12-31 | Under Construction
PRJ-MH-07 | Pandharpur Solar Irrigation Scheme | Maharashtra | Solapur | Solar | 35 | 175 | 2026-09-30 | Planning
PRJ-MH-08 | Sangli Surya Shakti Plant | Maharashtra | Sangli | Solar | 55 | 275 | 2025-06-30 | Land Acquisition
PRJ-KA-01 | Raichur Solar Ultra Mega Park | Karnataka | Raichur | Solar | 120 | 600 | 2025-06-30 | Under Construction
PRJ-KA-02 | Koppal Wind Power Station | Karnataka | Koppal | Wind | 90 | 540 | 2025-03-31 | Completed
PRJ-KA-03 | Kalaburagi Surya Urja Park | Karnataka | Kalaburagi | Solar | 85 | 425 | 2026-03-31 | Land Acquisition
PRJ-KA-04 | Vijayapura Solar Agri Initiative | Karnataka | Vijayapura | Solar | 65 | 325 | 2026-06-30 | Planning
PRJ-KA-05 | Bidar Renewable Energy Cluster | Karnataka | Bidar | Solar | 50 | 250 | 2025-09-30 | Land Acquisition
PRJ-KA-06 | Gadag Wind Farm Project | Karnataka | Gadag | Wind | 110 | 660 | 2025-12-31 | Under Construction
PRJ-KA-07 | Yadgir Sun Power Plant | Karnataka | Kalaburagi | Solar | 45 | 225 | 2026-09-30 | Planning
PRJ-KA-08 | Hospet Solar Power Station | Karnataka | Koppal | Solar | 70 | 350 | 2025-06-30 | Land Acquisition
[5 empty] | 1130 | 5930

## managment_summary
Solar Land Acquisition Monitoring Summary
Total Land Required (Acers) | 5930
Total Land Acquired (Parcel) | 59
Total Land Acquired (Acers) | 158
Pending Agreements | 128
Legal Verification Pending | 194
Payment Pending | 188
Land Acquisition Progress | 2.664%
Land Remaining | 5772
Agreement Executed Parcels | 119
Avg parcel Size | 2.8171

## pivot_analysis
Land Acquired by Project |  | Land Acquired by District
Registration_Status | Registered | Row Labels | Sum of Land_Area_Acres
|  | Bidar | 105.52
Row Labels | Sum of Land_Area_Acres | Gadag | 121.41
PRJ-KA-01 | 15.63 | Kalaburagi | 89.79
PRJ-KA-02 | 15.63 | Koppal | 117.09
PRJ-KA-03 | 1.95 | Latur | 146.89
PRJ-KA-04 | 3.88 | Nanded | 108.4
PRJ-KA-05 | 8.24 | Osmanabad | 185.64
PRJ-KA-06 | 6.33 | Pune | 172.57
PRJ-KA-07 | 17.07 | Raichur | 113.44
PRJ-KA-08 | 4.1 | Solapur | 157.08
PRJ-MH-01 | 7.63 | Vijayapura | 90.7
PRJ-MH-02 | 4.91 | Grand Total | 1408.53
PRJ-MH-03 | 11.74
PRJ-MH-04 | 7.3
PRJ-MH-05 | 15.16
PRJ-MH-06 | 18.05
PRJ-MH-07 | 11.6
PRJ-MH-08 | 8.78
Grand Total | 158
Agreement status |  | Payment Status Distribution
Row Labels | Count of Parcel_ID | Row Labels | Count of Parcel_ID
Agreement Executed | 119 | Unpaid | 188
MOU Signed | 121 | Advance Paid | 127
Not Started | 128 | Partially Paid | 121
Under Negotiation | 132 | Fully Paid | 64
Grand Total | 500 | Grand Total | 500